## wsr_26Jul19
Squaring & Corner Marking System Development Progress |  |  |  | 22-Jul-2019 to 26-Jul-2019
Task ID | Task Name | %Completion | Actual Effort Spent (Person Hours) during the reporting week | Remarks/Comments
5 | Developing routines for accessing other modules over serial communication | 90% | 4
14 | CAD for Laser measurement device enclosure | x
15 | CAD for laser measurement device on stepper motor fixture | x
19 | Developing routines for communicating measurements with master module over UART | 50% | 16
22 | Collect distance measurement data and generate report | ü | 6
23 | Develop handlers to data output commands (send data to mobile device) | 60% |  | Sending distance measurement data has been completed. Other event data sending to be implemented.
24 | Develop program to monitor battery levels | 30% | 4 | Hardware setup completed. Software implementation to be takenup
26 | CAD for laser reflector fixing on stepper motor | x
31 | Laser beacon assembly | 75% | 8 | Two beacons assembly completed. 3rd one to be assembled.
33 | CAD for laser beacon fixtures on the chassis | x
34 | CAD for chassis wheel motor driver fixture | x
35 | CAD for battery holder | x |  | Assembled battery on laser beacon temporarily
36 | CAD for MCU board fixture | x |  | Assembled MCU with generic adapter board and fixed on beacon and chassis
37 | CAD for Axi draw unit fixture | x |  | Not yet finalized the design
39 | Assembly of different parts of the aquaring and corner marking robot | 80% |  | Laser beacon assembly 50% done. Robotic chassis assembly 70% done Laser beacon home position detection done
42 | Power supply interfacing | ü | 8
43 | On-chassis Laser beacons interfacing | 75%
44 | Program to load layout dimensions from mobile BT terminal | 80% | 6
45 | Chassis control software interface (routines) development | 80% | 6
46 | Chassis forward movement control program development | 80% | 6
47 | Chassis backword movement control program development | 80% | 6
57 | Chassis alignment algorithm based on selected 1st corner | 25% | 16
| Hardware & Software porting for reducing BT devices on the chassis | ü | 16 | New hardware interface developed and to be replicated for India team

## wsr_19Jul19
Squaring & Corner Marking System Development Progress |  |  |  | 15-Jul-2019 to 19-Jul-2019
Task ID | Task Name | %Completion | Actual Effort Spent (Person Hours) during the reporting week | Remarks/Comments
5 | Developing routines for accessing other modules over serial communication | 75%
14 | CAD for Laser measurement device enclosure | x
15 | CAD for laser measurement device on stepper motor fixture | x
19 | Developing routines for communicating measurements with master module over UART | 25%
20 | Environment setup for distance measurement PoC task | ü | 4 | Temporarily fixed on wooden bases as demoed previously
21 | Performing laser based distance measurement using B87A laser device | ü | 20 | Measurements done upto 350'
22 | Collect distance measurement data and generate report
23 | Develop handlers to data output commands (send data to mobile device) | 60% |  | Sending distance measurement data has been completed. Other event data sending to be implemented.
24 | Develop program to monitor battery levels | x
26 | CAD for laser reflector fixing on stepper motor | x
31 | Laser beacon assembly | 50% | 6
33 | CAD for laser beacon fixtures on the chassis | x
34 | CAD for chassis wheel motor driver fixture | x
35 | CAD for battery holder | x | 4 | Assembled battery on laser beacon temporarily
36 | CAD for MCU board fixture | x | 6 | Assembled MCU with generic adapter board and fixed on beacon and chassis
37 | CAD for Axi draw unit fixture | x |  | Not yet finalized the design
39 | Assembly of different parts of the aquaring and corner marking robot | 80% |  | Laser beacon assembly 50% done. Robotic chassis assembly 70% done Laser beacon home position detection
42 | Power supply interfacing | 75%
43 | On-chassis Laser beacons interfacing | 75% | 8
44 | Program to load layout dimensions from mobile BT terminal | 50% | 8
45 | Chassis control software interface (routines) development | 50% | 8
46 | Chassis forward movement control program development | 50% | 8
47 | Chassis backword movement control program development | 50% | 8
| SMPS (24V/10Amp) purchase from local market | ü | 12 | One purchased was not functioning. Had to go back to the shop and get a replacement.
| Hardware & Software porting for reducing BT devices on the chassis | 50% | 8 | New hardware interface developed and to be replicated for India team
Note: | There was a week's delay in getting 8mm flanges. Not received till Friday. Had to redrill the 5mm hole to 8mm using drilling machine in-house for fixing laser on chassis. |  |  | Received the 8mm flanges today (22-Jul-2019)

## wsr_12Jul19
Squaring & Corner Marking System Development Progress |  |  |  | 01-Jul-2019 to 12-Jul-2019
Task ID | Task Name | %Completion | Actual Effort Spent (Person Hours) for the reporting week | Remarks/Comments
5 | Developing routines for accessing other modules over serial communication | 75%
14 | CAD for Laser measurement device enclosure | x
15 | CAD for laser measurement device on stepper motor fixture | x
19 | Developing routines for communicating measurements with master module over UART | 25% | 12
20 | Environment setup for distance measurement PoC task | 60% | 8 | Temporarily fixed on wooden bases as demoed previously
21 | Performing laser based distance measurement using B87A laser device | 60% | 8 | Could collect data for 14,15,20,25 meter distances
23 | Develop handlers to data output commands (send data to mobile device) | 60% | 16 | Sending distance measurement data has been completed. Other event data sending to be implemented.
24 | Develop program to monitor battery levels | x
26 | CAD for laser reflector fixing on stepper motor | x
28 | Laser Beacon base plate fabrication | ü | 8 | Base plates collected from the fabricator
33 | CAD for laser beacon fixtures on the chassis | x
34 | CAD for chassis wheel motor driver fixture | x
35 | CAD for battery holder | x | 8 | Assembled battery on laser beacon temporarily
36 | CAD for MCU board fixture | x | 8 | Assembled MCU with generic adapter board and fixed on beacon and chassis
39 | Assembly of different parts of the aquaring and corner marking robot | 80% | 16 | Laser beacon assembly 50% done. Robotic chassis assembly 70% done Laser beacon home position detection
40 | Stepper motor driver interfacing | ü
41 | MCU board interfacing | ü
42 | Power supply interfacing | 75% | 16

## wsr_05Jul19
Squaring & Corner Marking System Development Progress |  |  |  | 01-Jul-2019 to 05-Jul-2019
Task ID | Task Name | %Completion | Actual Effort Spent (Person Hours) for the reporting week | Remarks/Comments
4 | Study of nRF52840 board interfaces & functionality | ü | 4
5 | Developing routines for accessing other modules over serial communication | 75% | 6 | Commands to laser measurement device control, Chassis movement are implemented. Will be extended once, the integration is completed.
14 | CAD for Laser measurement device enclosure | x |  | Off the shelf box is being modified for now.
15 | CAD for laser measurement device on stepper motor fixture | x |  | Waiting for stepper motor flange (8mm).
16 | Study of B87A laser device specification | ü | 4 | Interface for working with measurement functionality completed. Other functionality for power optimization to be studied
17 | Study of B87A interfaces & functionality | ü | 2 | Interface for working with measurement functionality completed.
18 | Develop nRF52840 board initialization program | ü | 4
21 | Performing laser based distance measurement using B87A laser device | 40% | 8 | Waiting for base plates to arrive. The laser beam is not stable due to wind outdoors. Readings are not stable.
23 | Develop handlers to data output commands (send data to mobile device) | 50% |  | Sending distance measurement data has been completed. Other event data sending to be implemented.
24 | Develop program to monitor battery levels | x
26 | CAD for laser reflector fixing on stepper motor | x | 8 | Effort spent in customizing/fixing off the shelf box.
27 | Discussion with fabrication service providers | ü | 2 | The base plates are expected tomorrow
28 | Laser Beacon base plate fabrication |  |  | Expeted to complete tomorrow.
33 | CAD for laser beacon fixtures on the chassis | x | 16 | Custom fixtures are being used for functionality testing
34 | CAD for chassis wheel motor driver fixture | x | 4 | Custom fixtures are being used for functionality testing
38 | Fixtures fabrication & coordination with service provider | x |  | These fixtures will be designed and fabricated later
39 | Assembly of different parts of the aquaring and corner marking robot | 70% | 24 | Laser beacon assembly 50% done. Robotic chassis assembly 70% done
40 | Stepper motor driver interfacing | ü | 8
41 | MCU board interfacing | ü | 8
42 | Power supply interfacing | 50% | 4

## wsr_28Jun19
Squaring & Corner Marking System Development Progress |  |  |  | 19-Jun-2019 to 28-Jun-2019
Task ID | Task Name | %Completion | Effort Spent (Person Hours) | Remarks/Comments
2 | nRF52840 Board & B87A Laser board availability | ü | 0 | Available for both US & India teams
3 | Study of nRF52840 board specification | ü | 8
4 | Study of nRF52840 board interfaces & functionality | 70% | 8 | Able to interface with laser measurement device, stepper motor. Working on Chassis interfacing
5 | Developing routines for accessing other modules over serial communication | 50% | 16 | Able to interface with laser measurement device, stepper motor. Working on Chassis communication
6 | Develop program BT control program setup to communicate with mobie device over BT terminal | ü | 16
7 | Develop data receiver handler from BT | ü | 20
8 | Develop command parser program to identify the commands recived | ü | 20
9 | Develop program to parse the integer arguments | ü | 4
10 | Develop program to parse floatig point arguments | ü | 4
11 | Develop handlers to data input commands | ü | 20
12 | CAD for Laser Beacon base plate | ü | 20
13 | CAD for stepper motor on the base plate fixture | ü | 20
14 | CAD for Laser measurement device enclosure | x
15 | CAD for laser measurement device on stepper motor fixture | x
16 | Study of B87A laser device specification | 70% | 8 | Interface for working with measurement functionality completed. Other functionality for power optimization to be studied
17 | Study of B87A interfaces & functionality | 90% | 8 | Interface for working with measurement functionality completed.
18 | Develop nRF52840 board initialization program | 30% | 8
21 | Performing laser based distance measurement using B87A laser device | 30% | 20 | Basic measurements have been performed. Accuracy and repeatability tests to be performed. Able to measure accurately with ±1mm accuracy when measured upto 15' distance indoor. Working on settingup environment for measuring longer distances.
23 | Develop handlers to data output commands (send data to mobile device) | 50% | 8 | Sending distance measurement data has been completed. Other event data sending to be implemented.
27 | Discussion with fabrication service providers | In progress | 8 | Talking to different vendors is going on.

## MeasurementExp
Distance Mesured (mm)
S# | Manual | By JRT B87A Laser Device
| 1 | 1 | 2 | 3 | 4 | 5 | Avg.
1 | 3020 | 3019 | 3020 | 3020 | 3020 | 3021 | 3020
2 | 2275 | 2267 | 2267 | 2267 | 2268 | 2267 | 2267.2
3 | 1975 | 1975 | 1975 | 1976 | 1976 | 1976 | 1975.6
4 | 1675 | 1675 | 1675 | 1675 | 1675 | 1675 | 1675
5 | 1375 | 1374 | 1375 | 1375 | 1375 | 1375 | 1374.8
6 | 1075 | 1074 | 1074 | 1074 | 1075 | 1075 | 1074.4
7 | 775 | 774 | 774 | 774 | 774 | 774 | 774
8 | 475 | 473 | 473 | 473 | 473 | 472 | 472.8
9 | 175 | 169 | 169 | 169 | 169 | 169 | 169
10 | 75 | 73 | 72 | 73 | 73 | 72 | 72.6
11 | 50 | 47 | 47 | 48 | 48 | 48 | 47.6
12 | 25 | 25 | Sensor saturated
Distance Measured (mm)
S# | Manual | My JRT Laser
| 1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Avg. | Diff
1 | 15000 | 14995 | 14996 | 15000 | 14994 | 14999 | 14997 |  |  |  |  | 14996.8333 | -3.1667
|  | 14997 | 14997 | 14994 | 14996 | 14997 | 14995 |  |  |  |  | 14996 | -4
|  | 14994 | 14996 | 14994 | 14994 | 14997 | 14992 |  |  |  |  | 14994.5 | -5.5
|  | 14995 | 14999 | 14995 | 14996 | 14998 | 14996 | 14996 | 14999 | 14996 | 14999 | 14996.9 | -3.1
2 | 14000 | 13999 | 13994 | 13996 | 14000 | 13994 | 14009 | 14003 | 14003 | 13997 | 14008 | 14000.3 | 0.3
|  | 13996 | 14010 | 14001 | 14000 | 14004 | 14008 | 14007 | 13996 | 14003 | 13999 | 14002.4 | 2.4
|  | 13999 | 14000 | 14001 | 13999 | 14001 | 14002 | 14003 | 14006 | 13997 | 14006 | 14001.4 | 1.4
3 | 20000 | 19971 | 19977 | 19969 | 19969 | 19969 | 19972 | 19970 | 19971 | 19974 | 19966 | 19970.8 | -29.2
|  | 19971 | 19968 | 19966 | 19968 | 19972 | 19969 | 19968 | 19970 | 19969 | 19967 | 19968.8 | -31.2
|  | 19964 | 19973 | 19973 | 19976 | 19975 | 19964 | 19969 | 19974 | 19973 | 19972 | 19971.3 | -28.7
|  | 19969 | 19970 | 19972 | 19975 | 19971 | 19975 | 19974 | 19973 | 19971 | 19975 | 19972.5 | -27.5
|  | 19966 | 19969 | 19968 | 19970 | 19964 | 19968 | 19971 | 19974 | 19973 | 19965 | 19968.8 | -31.2
4 | 25000 | 25010 | 25006 | 24992 | 24998 | 24992 | 25007 | 25003 | 24995 | 25002 | 24995 | 25000 | 0
|  | 25010 | 25011 | 25000 | 24990 | 24985 | 25004 | 24998 | 24997 | 25012 | 24997 | 25000.4 | 0.4
Distance Measurement (mm)
Manual |  | JRT Laser Measurement
foot | mm | Fast Measurement Mode | [13 empty] | Slow Measurement Mode | [13 empty] | Auto Measurement Mode
1 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Min | Max | Avg | Diff | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Min | Max | Avg | Diff | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Min | Max | Avg | Diff
88' | 26822/PVC | 26961 | 26980 | 26979 | 26979 | 26977 | 26986 | 26975 | 26978 | 26978 | 26979 | 26961 | 26986 | 26977.2 | 25 | 26972 | 26972 | 26971 | 26974 | 26974 | 26974 | 26975 | 26976 | 26976 | 26976 | 26971 | 26976 | 26974 | 5 | 26967 | 26967 | 26968 | 26969 | 26980 | 26988 | 12209 | 26988 | 26988 | 26988
| 26822/WP | 26987 | 26987 | 26982 | 26982 | 26990 | 26987 | 26988 | 26975 | 26980 | 26978 | 26975 | 26990 | 26983.6 | 15 | 26973 | 26977 | 26979 | 26977 | 26976 | 26976 | 26973 | 26977 | 26977 | 26977 | 26973 | 26979 | 26976.2 | 6 | 26977 | 26981 | 26974 | 26974 | 26976 | 26979 | 26983 | 26979 | 26984 | 26982 | 26974 | 26984 | 26978.9 | 10
|  | 26979 | 26981 | 26981 | 26980 | 26973 | 26984 | 26970 | 26982 | 26982 | 26977 | 26970 | 26984 | 26978.9 | 14 | 26978 | 26980 | 26980 | 26979 | 26980 | 26978 | 26980 | 26979 | 26978 | 26982 | 26978 | 26982 | 26979.4 | 4 | 26977 | 26973 | 26976 | 26976 | 26981 | 26977 | 26979 | 26977 | 26976 | 26974 | 26973 | 26981 | 26976.6 | 8
| 26822/PVC | 26985 | 26977 | 26976 | 26980 | 26982 | 26980 | 26989 | 26979 | 26981 | 26984 | 26976 | 26989 | 26981.3 | 13 | 26982 | 26983 | 26983 | 26985 | 26981 | 26984 | 26984 | 26984 | 26981 | 26981 | 26981 | 26985 | 26982.8 | 4 | 26983 | 26982 | 26980 | 26982 | 26983 | 26984 | 26981 | 26984 | 26985 | 26986 | 26980 | 26986 | 26983 | 6
|  | 26988 | 26979 | 26985 | 26983 | 26981 | 26982 | 26978 | 26985 | 26982 | 26983 | 26978 | 26988 | 26982.6 | 10 | 26982 | 26980 | 26983 | 26982 | 26984 | 26983 | 26984 | 26982 | 26983 | 26982 | 26980 | 26984 | 26982.5 | 4 | 26981 | 26982 | 26983 | 26985 | 26984 | 26985 | 26986 | 26988 | 26982 | 26984 | 26981 | 26988 | 26984 | 7
|  | 26983 | 26978 | 26980 | 26986 | 26982 | 26981 | 26980 | 26983 | 26980 | 26975 | 26975 | 26986 | 26980.8 | 11 | 26981 | 26983 | 26982 | 26984 | 26982 | 26983 | 26982 | 26983 | 26983 | 26982 | 26981 | 26984 | 26982.5 | 3 | 26983 | 26988 | 26984 | 26980 | 26984 | 26984 | 26983 | 26983 | 26983 | 26983 | 26980 | 26988 | 26983.5 | 8
|  | 26985 | 26984 | 26984 | 26981 | 26982 | 26977 | 26986 | 26981 | 26980 | 26981 | 26977 | 26986 | 26982.1 | 9 | 26985 | 26983 | 26983 | 26983 | 26983 | 26984 | 26983 | 26984 | 26985 | 26984 | 26983 | 26985 | 26983.7 | 2 | 26981 | 26984 | 26984 | 26983 | 26981 | 26984 | 26984 | 26981 | 26982 | 26985 | 26981 | 26985 | 26982.9 | 4
|  | 26978 | 26984 | 26983 | 26985 | 26982 | 26983 | 26988 | 26981 | 26980 | 26980 | 26978 | 26988 | 26982.4 | 10 | 26983 | 26983 | 26983 | 26983 | 26985 | 26984 | 26985 | 26983 | 26983 | 26984 | 26983 | 26985 | 26983.6 | 2 | 26982 | 26985 | 26979 | 26983 | 26982 | 26982 | 26986 | 26985 | 26985 | 26987 | 26979 | 26987 | 26983.6 | 8
|  | 26985 | 26982 | 26979 | 26982 | 26985 | 26986 | 26985 | 26986 | 26983 | 26979 | 26979 | 26986 | 26983.2 | 7 | 26984 | 26983 | 26984 | 26984 | 26984 | 26983 | 26984 | 26983 | 26984 | 26983 | 26983 | 26984 | 26983.6 | 1 | 26983 | 26982 | 26982 | 26986 | 26984 | 26984 | 26983 | 26985 | 26985 | 26984 | 26982 | 26986 | 26983.8 | 4
100' | 30709 Reflector | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 0 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 0 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30666 | 30666 | 30665 | 30666 | 30665.2 | 1
|  | 30665 | 30665 | 30665 | 30666 | 30666 | 30666 | 30666 | 30666 | 30666 | 30666 | 30665 | 30666 | 30665.7 | 1 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30666 | 30666 | 30666 | 30666 | 30665 | 30666 | 30665.4 | 1 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 0
|  | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 0 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 0 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 30665 | 0
131' | 40157 Reflector | 39898 | 39898 | 39898 | 39898 | 39898 | 39898 | 39898 | 39898 | 39898 | 39897 | 39897 | 39898 | 39897.9 | 1 | 39897 | 39897 | 39897 | 39897 | 39897 | 39897 | 39898 | 39898 | 39898 | 39898 | 39897 | 39898 | 39897.4 | 1 | 39898 | 39898 | 39898 | 39898 | 39897 | 39897 | 39897 | 39897 | 39897 | 39897 | 39897 | 39898 | 39897.4 | 1
|  | 39897 | 39897 | 39897 | 39897 | 39897 | 39897 | 39897 | 39897 | 39897 | 39898 | 39897 | 39898 | 39897.1 | 1 | 39897 | 39897 | 39897 | 39897 | 39897 | 39897 | 39897 | 39898 | 39898 | 39898 | 39897 | 39898 | 39897.3 | 1 | 39898 | 39898 | 39898 | 39898 | 39898 | 39898 | 39898 | 39897 | 39897 | 39899 | 39897 | 39899 | 39897.9 | 2
|  | 39897 | 39897 | 39897 | 39897 | 39898 | 39898 | 39898 | 39898 | 39898 | 39899 | 39897 | 39899 | 39897.7 | 2 | 39897 | 39897 | 39897 | 39897 | 39897 | 39898 | 39898 | 39898 | 39898 | 39899 | 39897 | 39899 | 39897.6 | 2 | 39897 | 39897 | 39897 | 39897 | 39897 | 39897 | 39897 | 39897 | 39898 | 39898 | 39897 | 39898 | 39897.2 | 1
141' | 43205 Reflector | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 0 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 0 | 43327 | 43327 | 43327 | 43327 | 43328 | 43328 | 43328 | 43328 | 43328 | 43328 | 43327 | 43328 | 43327.6 | 1
|  | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 0 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 0 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 0
|  | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 0 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 0 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 43327 | 0
150'9" | 45949 | 45937 | 45938 | 45938 | 45939 | 45938 | 45939 | 45938 | 45938 | 45938 | 45938 | 45937 | 45939 | 45938.1 | 2 | 45938 | 45939 | 45939 | 45939 | 45939 | 45939 | 45939 | 45939 | 45939 | 45939 | 45938 | 45939 | 45938.9 | 1 | 45939 | 45939 | 45938 | 45938 | 45938 | 45939 | 45939 | 45939 | 45939 | 45939 | 45938 | 45939 | 45938.7 | 1
|  | 45939 | 45938 | 45938 | 45938 | 45939 | 45939 | 45938 | 45938 | 45938 | 45938 | 45938 | 45939 | 45938.3 | 1 | 45939 | 45939 | 45939 | 45939 | 45939 | 45939 | 45939 | 45939 | 45939 | 45940 | 45939 | 45940 | 45939.1 | 1 | 45938 | 45938 | 45938 | 45938 | 45938 | 45938 | 45938 | 45938 | 45938 | 45938 | 45938 | 45938 | 45938 | 0
|  | 45938 | 45938 | 45938 | 45938 | 45938 | 45938 | 45938 | 45938 | 45938 | 45938 | 45938 | 45938 | 45938 | 0 | 45939 | 45939 | 45939 | 45938 | 45938 | 45939 | 45939 | 45939 | 45939 | 45939 | 45938 | 45939 | 45938.8 | 1 | 45938 | 45938 | 45938 | 45938 | 45938 | 45938 | 45938 | 45938 | 45938 | 45938 | 45938 | 45938 | 45938 | 0
|  | 45938 | 45937 | 45939 | 45938 | 45938 | 45938 | 45938 | 45939 | 45939 | 45938 | 45937 | 45939 | 45938.2 | 2 | 45939 | 45939 | 45939 | 45939 | 45939 | 45939 | 45939 | 45939 | 45939 | 45940 | 45939 | 45940 | 45939.1 | 1 | 45939 | 45938 | 45938 | 45939 | 45939 | 45938 | 45938 | 45939 | 45938 | 45939 | 45938 | 45939 | 45938.5 | 1
|  | 45938 | 45938 | 45938 | 45938 | 45938 | 45938 | 45938 | 45938 | 45938 | 45938 | 45938 | 45938 | 45938 | 0 | 45937 | 45938 | 45938 | 45938 | 45938 | 45937 | 45937 | 45938 | 45938 | 45938 | 45937 | 45938 | 45937.7 | 1 | 45937 | 45938 | 45938 | 45938 | 45938 | 45938 | 45938 | 45938 | 45938 | 45938 | 45937 | 45938 | 45937.9 | 1
201'6" | 61417 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 0 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 0 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 0
|  | 61446 | 61447 | 61448 | 61448 | 61448 | 61448 | 61447 | 61448 | 61448 | 61448 | 61446 | 61448 | 61447.6 | 2 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61448 | 61448 | 61447 | 61448 | 61447.2 | 1 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 0
|  | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61448 | 61447 | 61448 | 61447.1 | 1 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 0 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61448 | 61447 | 61448 | 61447.1 | 1
|  | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 0 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 0 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61448 | 61448 | 61448 | 61448 | 61447 | 61448 | 61447.4 | 1
|  | 61446 | 61446 | 61446 | 61447 | 61447 | 61447 | 61447 | 61447 | 61448 | 61448 | 61446 | 61448 | 61446.9 | 2 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61448 | 61448 | 61448 | 61448 | 61447 | 61448 | 61447.4 | 1 | 61446 | 61446 | 61446 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61447 | 61446 | 61447 | 61446.7 | 1
251'6" | 76657 | 76644 | 76644 | 76644 | 76644 | 76644 | 76644 | 76644 | 76644 | 76643 | 76645 | 76643 | 76645 | 76644 | 2 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76642 | 76642 | 76643 | 76642.9 | 1 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76644 | 76643 | 76644 | 76643.1 | 1
|  | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 0 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 0 | 76644 | 76644 | 76644 | 76644 | 76644 | 76644 | 76644 | 76644 | 76644 | 76643 | 76643 | 76644 | 76643.9 | 1
|  | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76644 | 76644 | 76642 | 76642 | 76644 | 76643.1 | 2 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 0 | 76644 | 76644 | 76644 | 76645 | 76645 | 76645 | 76645 | 76645 | 76645 | 76646 | 76644 | 76646 | 76644.8 | 2
|  | 76643 | 76643 | 76643 | 76643 | 76643 | 76644 | 76644 | 76644 | 76644 | 76644 | 76643 | 76644 | 76643.5 | 1 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 76643 | 0 | 76646 | 76646 | 76646 | 76646 | 76646 | 76646 | 76646 | 76646 | 76646 | 76646 | 76646 | 76646 | 76646 | 0
|  | 76645 | 76645 | 76646 | 76646 | 76646 | 76646 | 76646 | 76646 | 76646 | 76647 | 76645 | 76647 | 76645.9 | 2 | 76646 | 76646 | 76646 | 76646 | 76646 | 76646 | 76646 | 76646 | 76646 | 76646 | 76646 | 76646 | 76646 | 0 | 76646 | 76646 | 76646 | 76646 | 76646 | 76646 | 76646 | 76646 | 76646 | 76646 | 76646 | 76646 | 76646 | 0
302'3" | 92123 | 92148 | 92148 | 92148 | 92148 | 92148 | 92148 | 92149 | 92149 | 92149 | 92149 | 92148 | 92149 | 92148.4 | 1 | 92148 | 92148 | 92148 | 92148 | 92148 | 92148 | 92148 | 92148 | 92148 | 92149 | 92148 | 92149 | 92148.1 | 1 | 92147 | 92147 | 92148 | 92148 | 92148 | 92148 | 92148 | 92148 | 92148 | 92148 | 92147 | 92148 | 92147.8 | 1
|  | 92146 | 92146 | 92146 | 92147 | 92147 | 92147 | 92148 | 92148 | 92148 | 92148 | 92146 | 92148 | 92147.1 | 2 | 92146 | 92147 | 92147 | 92147 | 92147 | 92147 | 92147 | 92148 | 92148 | 92148 | 92146 | 92148 | 92147.2 | 2 | 92146 | 92146 | 92146 | 92147 | 92147 | 92147 | 92147 | 92147 | 92148 | 92148 | 92146 | 92148 | 92146.9 | 2
|  | 92147 | 92147 | 92147 | 92147 | 92148 | 92148 | 92148 | 92148 | 92148 | 92149 | 92147 | 92149 | 92147.7 | 2 | 92147 | 92147 | 92147 | 92147 | 92147 | 92147 | 92147 | 92147 | 92147 | 92147 | 92147 | 92147 | 92147 | 0 | 92147 | 92147 | 92147 | 92147 | 92147 | 92147 | 92147 | 92147 | 92147 | 92148 | 92147 | 92148 | 92147.1 | 1
|  | 92146 | 92147 | 92147 | 92147 | 92148 | 92148 | 92148 | 92148 | 92148 | 92149 | 92146 | 92149 | 92147.6 | 3 | 92147 | 92147 | 92147 | 92147 | 92147 | 92147 | 92147 | 92147 | 92147 | 92147 | 92147 | 92147 | 92147 | 0 | 92147 | 92147 | 92148 | 92148 | 92148 | 92148 | 92148 | 92148 | 92149 | 92149 | 92147 | 92149 | 92148 | 2
|  | 92148 | 92148 | 92148 | 92148 | 92148 | 92148 | 92149 | 92149 | 92149 | 92149 | 92148 | 92149 | 92148.4 | 1 | 92148 | 92148 | 92148 | 92148 | 92148 | 92148 | 92148 | 92148 | 92148 | 92148 | 92148 | 92148 | 92148 | 0 | 92148 | 92148 | 92148 | 92148 | 92148 | 92148 | 92148 | 92148 | 92148 | 92148 | 92148 | 92148 | 92148 | 0
352'3" | 107366 | 107376 | 107376 | 107375 | 107375 | 107376 | 107376 | 107376 | 107375 | 107372 | 107376 | 107372 | 107376 | 107375.3 | 4 | 107377 | 107378 | 107378 | 107378 | 107378 | 107378 | 107378 | 107378 | 107378 | 107379 | 107377 | 107379 | 107378 | 2 | 107377 | 107377 | 107377 | 107377 | 107377 | 107377 | 107377 | 107377 | 107377 | 107377 | 107377 | 107377 | 107377 | 0
|  | 107377 | 107377 | 107377 | 107377 | 107378 | 107378 | 107378 | 107378 | 107379 | 107379 | 107377 | 107379 | 107377.8 | 2 | 107378 | 107378 | 107378 | 107379 | 107379 | 107379 | 107379 | 107379 | 107379 | 107379 | 107378 | 107379 | 107378.7 | 1 | 107375 | 107376 | 107376 | 107376 | 107376 | 107377 | 107378 | 107378 | 107378 | 107378 | 107375 | 107378 | 107376.8 | 3
|  | 107377 | 107377 | 107378 | 107378 | 107378 | 107378 | 107378 | 107378 | 107378 | 107378 | 107377 | 107378 | 107377.8 | 1 | 107378 | 107378 | 107378 | 107378 | 107378 | 107378 | 107378 | 107378 | 107378 | 107378 | 107378 | 107378 | 107378 | 0 | 107375 | 107376 | 107376 | 107376 | 107377 | 107377 | 107377 | 107377 | 107377 | 107377 | 107375 | 107377 | 107376.5 | 2
|  | 107377 | 107377 | 107377 | 107378 | 107378 | 107378 | 107378 | 107378 | 107378 | 107379 | 107377 | 107379 | 107377.8 | 2 | 107376 | 107377 | 107377 | 107377 | 107377 | 107378 | 107378 | 107378 | 107378 | 107378 | 107376 | 107378 | 107377.4 | 2 | 107376 | 107376 | 107376 | 107376 | 107376 | 107376 | 107376 | 107376 | 107377 | 107378 | 107376 | 107378 | 107376.3 | 2
|  | 107375 | 107376 | 107376 | 107377 | 107377 | 107377 | 107377 | 107378 | 107378 | 107378 | 107375 | 107378 | 107376.9 | 3 | 107376 | 107376 | 107376 | 107377 | 107377 | 107377 | 107377 | 107377 | 107377 | 107377 | 107376 | 107377 | 107376.7 | 1 | 107375 | 107375 | 107376 | 107376 | 107376 | 107376 | 107376 | 107376 | 107377 | 107377 | 107375 | 107377 | 107376 | 2
Observations:
1 | Upto 90', reflector is not needed. We may have to use PVC surface or white paper or any suitable laser reflecting surface
Little concerned about the deviations at shorter distances. Need to identify suitable reflector surface and repeat the experiments
2 | Above 90', reflector works well.
3 | 100' and above where reflector is used, the measurements are matching closely in all the three measurement modes

## SCMSDP-BL1
Squaring & Corner Marking System Development Plan |  |  | Version: | 1.0 | 2019-06-27 | [6 empty] | Status Tracking
S.No. | Task Name | Duration (Days) | Start Date | End Date | Total Effort (PH) | 264 |  | 476 |  | 446 |  | Cumm. Effort (PHs) | Actual Start Date | Actual End Date | Effort Spent (PHs) |  |  | % Completion | Net Days Gain/Lost | 29-Jul-19 to 02-Aug-19 |  | Remarks/Comments
[20 empty] | PHs | %
1 | Squaring and corner marking system development | 62 | 2019-06-19 08:00 | 2019-09-12 17:00 | 1186 | AK |  | BR |  | SB |  | 648 |  |  | AK | BR | SB
2 | nRF52840 Board & B87A Laser board availability | 0 | 2019-06-19 08:00 | 2019-06-19 08:00 | [7 empty] | 0 | [5 empty] | ü
3 | Study of nRF52840 board specification | 1 | 2019-06-19 08:00 | 2019-06-19 17:00 | 4 | 4 | 0.5 | 0 |  | 0 |  | 8 | [5 empty] | ü
4 | Study of nRF52840 board interfaces & functionality | 1 | 2019-06-20 08:00 | 2019-06-20 17:00 | 4 | 4 | 0.5 | 0 |  | 0 |  | 12 | [5 empty] | ü
5 | Developing routines for accessing other modules over serial communication | 3 | 2019-06-21 08:00 | 2019-06-25 17:00 | 12 | 12 | 0.5 | 0 |  | 0 |  | 26 | [5 empty] | 90%
6 | Develop program BT control program setup to communicate with mobie device over BT terminal | 3 | 2019-06-26 08:00 | 2019-06-28 17:00 | 12 | 12 | 0.5 | 0 |  | 0 |  | 16 | [5 empty] | ü
7 | Develop data receiver handler from BT | 2 | 2019-06-19 08:00 | 2019-06-20 17:00 | 16 | 0 |  | 0 |  | 16 | 1 | 20 | [5 empty] | ü
8 | Develop command parser program to identify the commands recived | 2 | 2019-06-21 08:00 | 2019-06-24 17:00 | 16 | 0 |  | 0 |  | 16 | 1 | 20 | [5 empty] | ü
9 | Develop program to parse the integer arguments | 1 | 2019-06-25 08:00 | 2019-06-25 17:00 | 8 | 0 |  | 0 |  | 8 | 1 | 4 | [5 empty] | ü
10 | Develop program to parse floatig point arguments | 1 | 2019-06-26 08:00 | 2019-06-26 17:00 | 8 | 0 |  | 0 |  | 8 | 1 | 4 | [5 empty] | ü
11 | Develop handlers to data input commands | 2 | 2019-06-27 08:00 | 2019-06-28 17:00 | 16 | 0 |  | 0 |  | 16 | 1 | 20 | [5 empty] | ü
12 | CAD for Laser Beacon base plate | 2 | 2019-06-19 08:00 | 2019-06-20 17:00 | 16 | 0 |  | 16 | 1 | 0 |  | 20 | [5 empty] | ü
13 | CAD for stepper motor on the base plate fixture | 2 | 2019-06-21 08:00 | 2019-06-24 17:00 | 16 | 0 |  | 16 | 1 | 0 |  | 20 | [5 empty] | ü
14 | CAD for Laser measurement device enclosure | 2 | 2019-06-25 08:00 | 2019-06-26 17:00 | 16 | 0 |  | 16 | 1 | 0 |  | 0 | [5 empty] | X
15 | CAD for laser measurement device on stepper motor fixture | 2 | 2019-06-27 08:00 | 2019-06-28 17:00 | 16 | 0 |  | 16 | 1 | 0 |  | 0 | [5 empty] | X
16 | Study of B87A laser device specification | 2 | 2019-07-01 08:00 | 2019-07-02 17:00 | 4 | 4 | 0.25 | 0 |  | 0 |  | 12 | [5 empty] | ü
17 | Study of B87A interfaces & functionality | 2 | 2019-07-03 08:00 | 2019-07-04 17:00 | 4 | 4 | 0.25 | 0 |  | 0 |  | 10 | [5 empty] | ü
18 | Develop nRF52840 board initialization program | 2 | 2019-07-05 08:00 | 2019-07-08 17:00 | 4 | 4 | 0.25 | 0 |  | 0 |  | 12 | [5 empty] | ü
19 | Developing routines for communicating measurements with master module over UART | 3 | 2019-07-09 08:00 | 2019-07-11 17:00 | 6 | 6 | 0.25 | 0 |  | 0 |  | 28 | [5 empty] | 50%
20 | Environment setup for distance measurement PoC task | 2 | 2019-07-12 08:00 | 2019-07-15 17:00 | 4 | 4 | 0.25 | 0 |  | 0 |  | 12 | [5 empty] | ü
21 | Performing laser based distance measurement using B87A laser device | 2 | 2019-07-16 08:00 | 2019-07-17 17:00 | 4 | 4 | 0.25 | 0 |  | 0 |  | 56 | [5 empty] | ü
22 | Collect distance measurement data and generate report | 1 | 2019-07-18 08:00 | 2019-07-18 17:00 | 2 | 2 | 0.25 | 0 |  | 0 |  | 6 | [5 empty] | ü
23 | Develop handlers to data output commands (send data to mobile device) | 2 | 2019-07-01 08:00 | 2019-07-02 17:00 | 8 | 0 |  | 0 |  | 8 | 0.5 | 24 | [5 empty] | 60%
24 | Develop program to monitor battery levels | 3 | 2019-07-03 08:00 | 2019-07-05 17:00 | 12 | 0 |  | 0 |  | 12 | 0.5 | 4 | [5 empty] | 30%
25 | Develop program to send alerts when events (battery low, marking corners finished) occur | 3 | 2019-07-08 08:00 | 2019-07-10 17:00 | 12 | 0 |  | 0 |  | 12 | 0.5 | 0 | [5 empty] | X
26 | CAD for laser reflector fixing on stepper motor | 2 | 2019-07-01 08:00 | 2019-07-02 17:00 | 8 | 0 |  | 8 | 0.5 | 0 |  | 8 | [5 empty] | X |  |  |  | Effort spent it custom arrangement
27 | Discussion with fabrication service providers | 2 | 2019-07-03 08:00 | 2019-07-04 17:00 | 8 | 0 |  | 8 | 0.5 | 0 |  | 10 | [5 empty] | ü
28 | Laser Beacon base plate fabrication | 2 | 2019-07-05 08:00 | 2019-07-08 17:00 | 8 | 0 |  | 8 | 0.5 | 0 |  | 8 | [5 empty] | ü
29 | B87A laser device enclosure fabrication | 2 | 2019-07-09 08:00 | 2019-07-10 17:00 | 8 | 0 |  | 8 | 0.5 | 0 |  | 0 | [5 empty] | X |  |  |  | Off the shelf enclosure used
30 | Cylindrical laser reflector fabrication | 2 | 2019-07-11 08:00 | 2019-07-12 17:00 | 8 | 0 |  | 8 | 0.5 | 0 |  | 0 | [5 empty] | X |  |  |  | Made reflector with custom assembly
31 | Laser beacon assembly | 2 | 2019-07-15 08:00 | 2019-07-16 17:00 | 8 | 0 |  | 8 | 0.5 | 0 |  | 14 | [5 empty] | 75
32 | Robotic chassis with mecanum wheels availability | 0 | 2019-07-02 17:00 | 2019-07-02 17:00 | 0 | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | ü
33 | CAD for laser beacon fixtures on the chassis | 2 | 2019-07-03 08:00 | 2019-07-04 17:00 | 8 | 0 |  | 8 | 0.5 | 0 |  | 16 | [5 empty] | X |  |  |  | Assembled with custom parts
34 | CAD for chassis wheel motor driver fixture | 2 | 2019-07-05 08:00 | 2019-07-08 17:00 | 8 | 0 |  | 8 | 0.5 | 0 |  | 4 | [5 empty] | X |  |  |  | Assembled with custom parts
35 | CAD for battery holder | 2 | 2019-07-09 08:00 | 2019-07-10 17:00 | 8 | 0 |  | 8 | 0.5 | 0 |  | 12 | [5 empty] | X |  |  |  | Assembled with custom parts
36 | CAD for MCU board fixture | 2 | 2019-07-11 08:00 | 2019-07-12 17:00 | 8 | 0 |  | 8 | 0.5 | 0 |  | 14 | [5 empty] | X |  |  |  | Assembled with custom parts
37 | CAD for Axi draw unit fixture | 2 | 2019-07-15 08:00 | 2019-07-16 17:00 | 8 | 0 |  | 8 | 0.5 | 0 |  | 0 | [5 empty] | X
38 | Fixtures fabrication & coordination with service provider | 2 | 2019-07-05 08:00 | 2019-07-08 17:00 | 8 | 0 |  | 8 | 0.5 | 0 |  | 0 | [5 empty] | X |  |  |  | Assembled with custom parts
39 | Assembly of different parts of the aquaring and corner marking robot | 1 | 2019-07-09 08:00 | 2019-07-09 17:00 | 4 | 0 |  | 4 | 0.5 | 0 |  | 40 | [5 empty] | 80%
40 | Stepper motor driver interfacing | 1 | 2019-07-10 08:00 | 2019-07-10 17:00 | 8 | 4 | 0.5 | 0 |  | 4 | 0.5 | 8 | [5 empty] | ü
41 | MCU board interfacing | 1 | 2019-07-11 08:00 | 2019-07-11 17:00 | 8 | 4 | 0.5 | 0 |  | 4 | 0.5 | 8 | [5 empty] | ü
42 | Power supply interfacing | 1 | 2019-07-12 08:00 | 2019-07-12 17:00 | 8 | 4 | 0.5 | 0 |  | 4 | 0.5 | 28 | [5 empty] | ü
43 | On-chassis Laser beacons interfacing | 1 | 2019-07-15 08:00 | 2019-07-15 17:00 | 8 | 4 | 0.5 | 0 |  | 4 | 0.5 | 8 | [5 empty] | 75%
44 | Program to load layout dimensions from mobile BT terminal | 1 | 2019-07-16 08:00 | 2019-07-16 17:00 | 16 | 4 | 0.5 | 4 | 0.5 | 8 | 1 | 18 |  |  |  |  | 4 | ü |  | 4 | 20%
45 | Chassis control software interface (routines) development | 1 | 2019-07-17 08:00 | 2019-07-17 17:00 | 16 | 4 | 0.5 | 4 | 0.5 | 8 | 1 | 18 |  |  |  |  | 4 | ü |  | 4 | 20%
46 | Chassis forward movement control program development | 1 | 2019-07-18 08:00 | 2019-07-18 17:00 | 16 | 4 | 0.5 | 4 | 0.5 | 8 | 1 | 18 |  |  |  |  | 4 | ü |  | 4 | 20%
47 | Chassis backword movement control program development | 1 | 2019-07-19 08:00 | 2019-07-19 17:00 | 16 | 4 | 0.5 | 4 | 0.5 | 8 | 1 | 18 |  |  |  |  | 4 | ü |  | 4 | 20%
48 | Chassis left side movement control program development | 1 | 2019-07-22 08:00 | 2019-07-22 17:00 | 16 | 4 | 0.5 | 4 | 0.5 | 8 | 1 | 8 |  |  | 4 | 4 |  | 50% |  | 8 | 50%
49 | Chassis right side movement control program development | 1 | 2019-07-23 08:00 | 2019-07-23 17:00 | 16 | 4 | 0.5 | 4 | 0.5 | 8 | 1 | 8 |  |  | 4 | 4 |  | 50% |  | 8 | 50%
50 | Chassis diagonal movement control program development | 1 | 2019-07-24 08:00 | 2019-07-24 17:00 | 16 | 4 | 0.5 | 4 | 0.5 | 8 | 1 | 8 |  |  | 4 | 4 |  | 50% |  | 8 | 50%
51 | Chassis algnment laser beacons control program development | 3 | 2019-07-25 08:00 | 2019-07-29 17:00 | 24 | 12 | 0.5 | 0 |  | 12 | 0.5 | 8 |  |  | 4 | 4 |  | 50% |  | 8 | 50%
52 | On chassis primary distance measurement laser control program development | 2 | 2019-07-30 08:00 | 2019-07-31 17:00 | 16 | 8 | 0.5 | 0 |  | 8 | 0.5 | 8 |  |  | 4 | 4 |  | 50% |  | 8 | 50%
53 | System level test plan development | 3 | 2019-07-16 08:00 | 2019-07-18 17:00 | 24 | 0 |  | 12 | 0.5 | 12 | 0.5 | 0 | [5 empty] | X
54 | System level test specification | 3 | 2019-07-19 08:00 | 2019-07-23 17:00 | 24 | 0 |  | 12 | 0.5 | 12 | 0.5 | 0 | [5 empty] | X
55 | System level test environment creation | 3 | 2019-07-24 08:00 | 2019-07-26 17:00 | 24 | 0 |  | 12 | 0.5 | 12 | 0.5 | 0 | [5 empty] | X
56 | Laser beacon subsystem testing | 3 | 2019-07-17 08:00 | 2019-07-19 17:00 | 24 | 0 |  | 12 | 0.5 | 12 | 0.5 | 0 | [5 empty] | X
57 | Chassis alignment algorithm based on selected 1st corner | 3 | 2019-08-01 08:00 | 2019-08-05 17:00 | 36 | 12 | 0.5 | 12 | 0.5 | 12 | 0.5 | 24 |  |  |  | 12 |  | 50% |  | 12 | 25%
58 | Triangulation algorithm development to reach the desired 2nd corner | 2 | 2019-08-06 08:00 | 2019-08-07 17:00 | 24 | 8 | 0.5 | 8 | 0.5 | 8 | 0.5
59 | Robot movement control algorithm for reaching 2nd corner | 2 | 2019-08-08 08:00 | 2019-08-09 17:00 | 24 | 8 | 0.5 | 8 | 0.5 | 8 | 0.5
60 | Axi draw control program to mark two punch holes for fixing laser beacon | 2 | 2019-08-12 08:00 | 2019-08-13 17:00 | 24 | 8 | 0.5 | 8 | 0.5 | 8 | 0.5
61 | Triangulation algorithm development to reach the desired 3rd corner | 2 | 2019-08-01 08:00 | 2019-08-02 17:00 | 24 | 8 | 0.5 | 8 | 0.5 | 8 | 0.5
62 | Robot movement control algorithm for reaching 3rd corner | 1 | 2019-08-05 08:00 | 2019-08-05 17:00 | 12 | 4 | 0.5 | 4 | 0.5 | 4 | 0.5
63 | Axi draw control program to mark two puch holes for fixing laser beacon | 1 | 2019-08-06 08:00 | 2019-08-06 17:00 | 12 | 4 | 0.5 | 4 | 0.5 | 4 | 0.5
64 | Triangulation algorithm development to reach the desired 4th corner | 2 | 2019-08-07 08:00 | 2019-08-08 17:00 | 24 | 8 | 0.5 | 8 | 0.5 | 8 | 0.5
65 | Robot movement control algorithm for reaching 4th corner | 1 | 2019-08-09 08:00 | 2019-08-09 17:00 | 12 | 4 | 0.5 | 4 | 0.5 | 4 | 0.5
66 | Axi draw control program to mark two punch holes for fixing laser beacon | 1 | 2019-08-12 08:00 | 2019-08-12 17:00 | 12 | 4 | 0.5 | 4 | 0.5 | 4 | 0.5
67 | Integrate dimensions loading program module | 1 | 2019-08-13 08:00 | 2019-08-13 17:00 | 10 | 2 | 0.25 | 4 | 0.5 | 4 | 0.5
68 | Integrate chassis movement control program module | 1 | 2019-08-14 08:00 | 2019-08-14 17:00 | 14 | 2 | 0.25 | 8 | 1 | 4 | 0.5
69 | Integrate on-chassis laser beacons control program module | 1 | 2019-08-15 08:00 | 2019-08-15 17:00 | 14 | 2 | 0.25 | 8 | 1 | 4 | 0.5
70 | Integrate 2nd corner marking program module | 1 | 2019-08-16 08:00 | 2019-08-16 17:00 | 14 | 2 | 0.25 | 8 | 1 | 4 | 0.5
71 | Test the functionality integrated so far | 1 | 2019-08-19 08:00 | 2019-08-19 17:00 | 14 | 2 | 0.25 | 8 | 1 | 4 | 0.5
72 | Integrate 3rd corner marking program module | 1 | 2019-08-20 08:00 | 2019-08-20 17:00 | 14 | 2 | 0.25 | 8 | 1 | 4 | 0.5
73 | Test the functionality after 3rd corner marking program integration | 1 | 2019-08-21 08:00 | 2019-08-21 17:00 | 14 | 2 | 0.25 | 8 | 1 | 4 | 0.5
74 | Integrate 4th corner marking program module | 1 | 2019-08-22 08:00 | 2019-08-22 17:00 | 14 | 2 | 0.25 | 8 | 1 | 4 | 0.5
75 | Test the functionality after 4th corner marking program integration | 3 | 2019-08-23 08:00 | 2019-08-27 17:00 | 24 | 6 | 0.25 | 6 | 0.25 | 12 | 0.5
76 | Robotic chassis subsystem testing | 3 | 2019-08-28 08:00 | 2019-08-30 | 30 | 0 |  | 6 | 0.25 | 24 | 1
77 | Laser Beacon user documentation | 3 | 2019-08-28 08:00 | 2019-08-30 17:00 | 24 | 0 |  | 24 | 1 | 0
78 | Robotic chassis subsystem testing | 1 | 2019-09-02 | 2019-09-02 | 10 | 0 |  | 2 | 0.25 | 8 | 1
79 | Combined system level testing | 5 | 2019-09-03 08:00 | 2019-09-09 17:00 | 60 | 20 | 0.5 | 10 | 0.25 | 30 | 0.75
80 | Test analysis, retesting & performance report | 3 | 2019-09-10 08:00 | 2019-09-12 17:00 | 36 | 12 | 0.5 | 6 | 0.25 | 18 | 0.75
81 | Robot chassis user documentation | 4 | 2019-09-02 08:00 | 2019-09-05 17:00 | 40 | 8 | 0.25 | 24 | 0.75 | 8 | 0.25
82 | Squaring & corner marking system user documentation | 5 | 2019-09-06 08:00 | 2019-09-12 17:00 | 50 | 10 | 0.25 | 30 | 0.75 | 10 | 0.25
|  | Total Planned Effort (PHs) |  |  | 1186 | [6 empty] | Planned Person Hours Remaining at the end of reporting week | [6 empty] | -12
Unexpected taskes taken up
X01 | SMPS (24V/10Amp) purchase from local market |  |  |  | 0 | [6 empty] | 12
X02 | Hardware & Software porting for reducing BT devices on the chassis |  |  |  | 0 | [6 empty] | 24 | [5 empty] | ü
X03 | PC based GUI app development |  |  |  | 0 | [6 empty] | 16 | 2019-07-30 | 2019-07-31 |  |  | 16 | 40% |  | 16 | 40%
[15 empty] | Reporting Week (PHs) |  |  |  |  | 84

## SCMSDP1
Squaring & Corner Marking System Development Plan |  |  | Version: | 0.2 | 2019-06-21
S.No. | Task Name | Duration (Days) | Start Date | End Date | Total Effort (Person Hours) | 264 |  | 476 |  | 446 |  | 264
1 | Squaring and corner marking system development | 62 | 2019-06-19 08:00 | 2019-09-12 17:00 | 1450 | AK |  | BR |  | SB |  | BG
2 | Laser Based Distance Measurement PoC | 22 | 2019-06-19 08:00 | 2019-07-18 17:00
3 | nRF52840 Board & B707C Laser board availability | 0 | 2019-06-19 08:00 | 2019-06-19 08:00
4 | Study of nRF52840 board specification | 1 | 2019-06-19 08:00 | 2019-06-19 17:00 | 8 | 4 | 0.5 | 0 |  | 0 |  | 4 | 0.5
5 | Study of nRF52840 board interfaces & functionality | 1 | 2019-06-20 08:00 | 2019-06-20 17:00 | 8 | 4 | 0.5 | 0 |  | 0 |  | 4 | 0.5
6 | Developing routines for accessing other modules over serial communication | 3 | 2019-06-21 08:00 | 2019-06-25 17:00 | 24 | 12 | 0.5 | 0 |  | 0 |  | 12 | 0.5
7 | Develop program BT control program setup to communicate with mobie device over BT terminal | 3 | 2019-06-26 08:00 | 2019-06-28 17:00 | 24 | 12 | 0.5 | 0 |  | 0 |  | 12 | 0.5
8 | Study of B707C laser device specification | 2 | 2019-07-01 08:00 | 2019-07-02 17:00 | 12 | 4 | 0.25 | 0 |  | 0 |  | 8 | 0.5
9 | Study of B707C interfaces & functionality | 2 | 2019-07-03 08:00 | 2019-07-04 17:00 | 12 | 4 | 0.25 | 0 |  | 0 |  | 8 | 0.5
10 | Develop nRF52840 board initialization program | 2 | 2019-07-05 08:00 | 2019-07-08 17:00 | 12 | 4 | 0.25 | 0 |  | 0 |  | 8 | 0.5
11 | Developing routines for communicating measurements with master module over UART | 3 | 2019-07-09 08:00 | 2019-07-11 17:00 | 18 | 6 | 0.25 | 0 |  | 0 |  | 12 | 0.5
12 | Environment setup for distance measurement PoC task | 2 | 2019-07-12 08:00 | 2019-07-15 17:00 | 12 | 4 | 0.25 | 0 |  | 0 |  | 8 | 0.5
13 | Performing laser based distance measurement using B707C laser device | 2 | 2019-07-16 08:00 | 2019-07-17 17:00 | 12 | 4 | 0.25 | 0 |  | 0 |  | 8 | 0.5
14 | Collect distance measurement data and generate report | 1 | 2019-07-18 08:00 | 2019-07-18 17:00 | 6 | 2 | 0.25 | 0 |  | 0 |  | 4 | 0.5
15 | Serial monitor and command parser for controlling from mobile BT terminal | 16 | 2019-06-19 08:00 | 2019-07-10 17:00
16 | Develop data receiver handler from BT | 2 | 2019-06-19 08:00 | 2019-06-20 17:00 | 16 | 0 |  | 0 |  | 16 | 1 | 0
17 | Develop command parser program to identify the commands recived | 2 | 2019-06-21 08:00 | 2019-06-24 17:00 | 16 | 0 |  | 0 |  | 16 | 1 | 0
18 | Develop program to parse the integer arguments | 1 | 2019-06-25 08:00 | 2019-06-25 17:00 | 8 | 0 |  | 0 |  | 8 | 1 | 0
19 | Develop program to parse floatig point arguments | 1 | 2019-06-26 08:00 | 2019-06-26 17:00 | 8 | 0 |  | 0 |  | 8 | 1 | 0
20 | Develop handlers to data input commands | 2 | 2019-06-27 08:00 | 2019-06-28 17:00 | 16 | 0 |  | 0 |  | 16 | 1 | 0
21 | Develop handlers to data output commands (send data to mobile device) | 2 | 2019-07-01 08:00 | 2019-07-02 17:00 | 8 | 0 |  | 0 |  | 8 | 0.5 | 0
22 | Develop program to monitor battery levels | 3 | 2019-07-03 08:00 | 2019-07-05 17:00 | 12 | 0 |  | 0 |  | 12 | 0.5 | 0
23 | Develop program to send alerts when events (battery low, marking corners finished) occur | 3 | 2019-07-08 08:00 | 2019-07-10 17:00 | 12 | 0 |  | 0 |  | 12 | 0.5 | 0
24 | CAD for Laser Beacon | 20 | 2019-06-19 08:00 | 2019-07-16 17:00
25 | CAD for Laser Beacon base plate | 2 | 2019-06-19 08:00 | 2019-06-20 17:00 | 16 | 0 |  | 16 | 1 | 0 |  | 0
26 | CAD for stepper motor on the base plate fixture | 2 | 2019-06-21 08:00 | 2019-06-24 17:00 | 16 | 0 |  | 16 | 1 | 0 |  | 0
27 | CAD for Laser measurement device enclosure | 2 | 2019-06-25 08:00 | 2019-06-26 17:00 | 16 | 0 |  | 16 | 1 | 0 |  | 0
28 | CAD for laser measurement device on stepper motor fixture | 2 | 2019-06-27 08:00 | 2019-06-28 17:00 | 16 | 0 |  | 16 | 1 | 0 |  | 0
29 | CAD for laser reflector fixing on stepper motor | 2 | 2019-07-01 08:00 | 2019-07-02 17:00 | 8 | 0 |  | 8 | 0.5 | 0 |  | 0
30 | Discussion with fabrication service providers | 2 | 2019-07-03 08:00 | 2019-07-04 17:00 | 8 | 0 |  | 8 | 0.5 | 0 |  | 0
31 | Laser Beacon base plate fabrication | 2 | 2019-07-05 08:00 | 2019-07-08 17:00 | 8 | 0 |  | 8 | 0.5 | 0 |  | 0
32 | B707C laser device enclosure fabrication | 2 | 2019-07-09 08:00 | 2019-07-10 17:00 | 8 | 0 |  | 8 | 0.5 | 0 |  | 0
33 | Cylindrical laser reflector fabrication | 2 | 2019-07-11 08:00 | 2019-07-12 17:00 | 8 | 0 |  | 8 | 0.5 | 0 |  | 0
34 | Laser beacon assembly | 2 | 2019-07-15 08:00 | 2019-07-16 17:00 | 8 | 0 |  | 8 | 0.5 | 0 |  | 0
35 | Squaring and corner marking robot mechanical hardware design | 10 | 2019-07-02 17:00 | 2019-07-16 17:00
36 | Robotic chassis with mecanum wheels availability | 0 | 2019-07-02 17:00 | 2019-07-02 17:00 | 0 | 0 |  | 0 |  | 0 |  | 0
37 | CAD for fixtures to fit other parts on robotic chassis | 10 | 2019-07-03 08:00 | 2019-07-16 17:00
38 | CAD for laser beacon fixtures on the chassis | 2 | 2019-07-03 08:00 | 2019-07-04 17:00 | 8 | 0 |  | 8 | 0.5 | 0 |  | 0
39 | CAD for chassis wheel motor driver fixture | 2 | 2019-07-05 08:00 | 2019-07-08 17:00 | 8 | 0 |  | 8 | 0.5 | 0 |  | 0
40 | CAD for battery holder | 2 | 2019-07-09 08:00 | 2019-07-10 17:00 | 8 | 0 |  | 8 | 0.5 | 0 |  | 0
41 | CAD for MCU board fixture | 2 | 2019-07-11 08:00 | 2019-07-12 17:00 | 8 | 0 |  | 8 | 0.5 | 0 |  | 0
42 | CAD for Axi draw unit fixture | 2 | 2019-07-15 08:00 | 2019-07-16 17:00 | 8 | 0 |  | 8 | 0.5 | 0 |  | 0
43 | Fixtures fabrication & coordination with service provider | 2 | 2019-07-05 08:00 | 2019-07-08 17:00 | 8 | 0 |  | 8 | 0.5 | 0 |  | 0
44 | Assembly of different parts of the aquaring and corner marking robot | 1 | 2019-07-09 08:00 | 2019-07-09 17:00 | 4 | 0 |  | 4 | 0.5 | 0 |  | 0
45 | Squaring and corner marking robot electronic hardware integration | 4 | 2019-07-10 08:00 | 2019-07-15 17:00
46 | Stepper motor driver interfacing | 1 | 2019-07-10 08:00 | 2019-07-10 17:00 | 8 | 4 | 0.5 | 0 |  | 4 | 0.5 | 0
47 | MCU board interfacing | 1 | 2019-07-11 08:00 | 2019-07-11 17:00 | 8 | 4 | 0.5 | 0 |  | 4 | 0.5 | 0
48 | Power supply interfacing | 1 | 2019-07-12 08:00 | 2019-07-12 17:00 | 8 | 4 | 0.5 | 0 |  | 4 | 0.5 | 0
49 | On-chassis Laser beacons interfacing | 1 | 2019-07-15 08:00 | 2019-07-15 17:00 | 8 | 4 | 0.5 | 0 |  | 4 | 0.5 | 0
50 | Squaring and corner marking robot control software development | 21 | 2019-07-16 08:00 | 2019-08-13 17:00 |  | 0 |  | 0 |  | 0 |  | 0
51 | Robotic chassis movement control program development | 7 | 2019-07-16 08:00 | 2019-07-24 17:00
52 | Program to load layout dimensions from mobile BT terminal | 1 | 2019-07-16 08:00 | 2019-07-16 17:00 | 16 | 4 | 0.5 | 4 | 0.5 | 8 | 1 | 0
53 | Chassis control software interface (routines) development | 1 | 2019-07-17 08:00 | 2019-07-17 17:00 | 16 | 4 | 0.5 | 4 | 0.5 | 8 | 1 | 0
54 | Chassis forward movement control program development | 1 | 2019-07-18 08:00 | 2019-07-18 17:00 | 16 | 4 | 0.5 | 4 | 0.5 | 8 | 1 | 0
55 | Chassis backword movement control program development | 1 | 2019-07-19 08:00 | 2019-07-19 17:00 | 16 | 4 | 0.5 | 4 | 0.5 | 8 | 1 | 0
56 | Chassis left side movement control program development | 1 | 2019-07-22 08:00 | 2019-07-22 17:00 | 16 | 4 | 0.5 | 4 | 0.5 | 8 | 1 | 0
57 | Chassis right side movement control program development | 1 | 2019-07-23 08:00 | 2019-07-23 17:00 | 16 | 4 | 0.5 | 4 | 0.5 | 8 | 1 | 0
58 | Chassis diagonal movement control program development | 1 | 2019-07-24 08:00 | 2019-07-24 17:00 | 16 | 4 | 0.5 | 4 | 0.5 | 8 | 1 | 0
59 | On chassis laser beacons control program development | 5 | 2019-07-25 08:00 | 2019-07-31 17:00
60 | Chassis algnment laser beacons control program development | 3 | 2019-07-25 08:00 | 2019-07-29 17:00 | 24 | 12 | 0.5 | 0 |  | 12 | 0.5 | 0
61 | On chassis primary distance measurement laser control program development | 2 | 2019-07-30 08:00 | 2019-07-31 17:00 | 16 | 8 | 0.5 | 0 |  | 8 | 0.5 | 0
62 | Algorithm for 2nd corner marking | 9 | 2019-08-01 08:00 | 2019-08-13 17:00
63 | Chassis alignment algorithm based on selected 1st corner | 3 | 2019-08-01 08:00 | 2019-08-05 17:00 | 48 | 12 | 0.5 | 12 | 0.5 | 12 | 0.5 | 12 | 0.5
64 | Triangulation algorithm development to reach the desired 2nd corner | 2 | 2019-08-06 08:00 | 2019-08-07 17:00 | 32 | 8 | 0.5 | 8 | 0.5 | 8 | 0.5 | 8 | 0.5
65 | Robot movement control algorithm for reaching 2nd corner | 2 | 2019-08-08 08:00 | 2019-08-09 17:00 | 32 | 8 | 0.5 | 8 | 0.5 | 8 | 0.5 | 8 | 0.5
66 | Axi draw control program to mark two punch holes for fixing laser beacon | 2 | 2019-08-12 08:00 | 2019-08-13 17:00 | 32 | 8 | 0.5 | 8 | 0.5 | 8 | 0.5 | 8 | 0.5
67 | Algorithm for 3rd corner marking | 4 | 2019-08-01 08:00 | 2019-08-06 17:00
68 | Triangulation algorithm development to reach the desired 3rd corner | 2 | 2019-08-01 08:00 | 2019-08-02 17:00 | 24 | 8 | 0.5 | 8 | 0.5 | 8 | 0.5 | 0
69 | Robot movement control algorithm for reaching 3rd corner | 1 | 2019-08-05 08:00 | 2019-08-05 17:00 | 12 | 4 | 0.5 | 4 | 0.5 | 4 | 0.5 | 0
70 | Axi draw control program to mark two puch holes for fixing laser beacon | 1 | 2019-08-06 08:00 | 2019-08-06 17:00 | 12 | 4 | 0.5 | 4 | 0.5 | 4 | 0.5 | 0
71 | Algorithm for 4th corner marking | 4 | 2019-08-07 08:00 | 2019-08-12 17:00
72 | Triangulation algorithm development to reach the desired 4th corner | 2 | 2019-08-07 08:00 | 2019-08-08 17:00 | 24 | 8 | 0.5 | 8 | 0.5 | 8 | 0.5 | 0
73 | Robot movement control algorithm for reaching 4th corner | 1 | 2019-08-09 08:00 | 2019-08-09 17:00 | 12 | 4 | 0.5 | 4 | 0.5 | 4 | 0.5 | 0
74 | Axi draw control program to mark two punch holes for fixing laser beacon | 1 | 2019-08-12 08:00 | 2019-08-12 17:00 | 12 | 4 | 0.5 | 4 | 0.5 | 4 | 0.5 | 0
75 | Squaring and corner marking robot integration | 11 | 2019-08-13 08:00 | 2019-08-27 17:00
76 | Integrate dimensions loading program module | 1 | 2019-08-13 08:00 | 2019-08-13 17:00 | 14 | 2 | 0.25 | 4 | 0.5 | 4 | 0.5 | 4 | 0.5
77 | Integrate chassis movement control program module | 1 | 2019-08-14 08:00 | 2019-08-14 17:00 | 18 | 2 | 0.25 | 8 | 1 | 4 | 0.5 | 4 | 0.5
78 | Integrate on-chassis laser beacons control program module | 1 | 2019-08-15 08:00 | 2019-08-15 17:00 | 18 | 2 | 0.25 | 8 | 1 | 4 | 0.5 | 4 | 0.5
79 | Integrate 2nd corner marking program module | 1 | 2019-08-16 08:00 | 2019-08-16 17:00 | 18 | 2 | 0.25 | 8 | 1 | 4 | 0.5 | 4 | 0.5
80 | Test the functionality integrated so far | 1 | 2019-08-19 08:00 | 2019-08-19 17:00 | 18 | 2 | 0.25 | 8 | 1 | 4 | 0.5 | 4 | 0.5
81 | Integrate 3rd corner marking program module | 1 | 2019-08-20 08:00 | 2019-08-20 17:00 | 18 | 2 | 0.25 | 8 | 1 | 4 | 0.5 | 4 | 0.5
82 | Test the functionality after 3rd corner marking program integration | 1 | 2019-08-21 08:00 | 2019-08-21 17:00 | 18 | 2 | 0.25 | 8 | 1 | 4 | 0.5 | 4 | 0.5
83 | Integrate 4th corner marking program module | 1 | 2019-08-22 08:00 | 2019-08-22 17:00 | 18 | 2 | 0.25 | 8 | 1 | 4 | 0.5 | 4 | 0.5
84 | Test the functionality after 4th corner marking program integration | 3 | 2019-08-23 08:00 | 2019-08-27 17:00 | 36 | 6 | 0.25 | 6 | 0.25 | 12 | 0.5 | 12 | 0.5
85 | Squaring and corner marking robot system testing | 43 | 2019-07-16 08:00 | 2019-09-12 17:00
86 | System level test plan development | 3 | 2019-07-16 08:00 | 2019-07-18 17:00 | 24 | 0 |  | 12 | 0.5 | 12 | 0.5 | 0
87 | System level test specification | 3 | 2019-07-19 08:00 | 2019-07-23 17:00 | 36 | 0 |  | 12 | 0.5 | 12 | 0.5 | 12 | 0.5
88 | System level test environment creation | 3 | 2019-07-24 08:00 | 2019-07-26 17:00 | 36 | 0 |  | 12 | 0.5 | 12 | 0.5 | 12 | 0.5
89 | Laser beacon subsystem testing | 3 | 2019-07-17 08:00 | 2019-07-19 17:00 | 36 | 0 |  | 12 | 0.5 | 12 | 0.5 | 12 | 0.5
90 | Robotic chassis subsystem testing | 4 | 2019-08-28 08:00 | 2019-09-02 17:00 | 56 | 0 |  | 8 | 0.25 | 32 | 1 | 16 | 0.5
91 | Combined system level testing | 5 | 2019-09-03 08:00 | 2019-09-09 17:00 | 80 | 20 | 0.5 | 10 | 0.25 | 30 | 0.75 | 20 | 0.5
92 | Test analysis, retesting & performance report | 3 | 2019-09-10 08:00 | 2019-09-12 17:00 | 42 | 12 | 0.5 | 6 | 0.25 | 18 | 0.75 | 6 | 0.25
93 | Documentation and User manuals | 12 | 2019-08-28 08:00 | 2019-09-12 17:00
94 | Laser Beacon user documentation | 3 | 2019-08-28 08:00 | 2019-08-30 17:00 | 24 | 0 |  | 24 | 1 | 0 |  | 0
95 | Robot chassis user documentation | 4 | 2019-09-02 08:00 | 2019-09-05 17:00 | 48 | 8 | 0.25 | 24 | 0.75 | 8 | 0.25 | 8 | 0.25
96 | Squaring & corner marking system user documentation | 5 | 2019-09-06 08:00 | 2019-09-12 17:00 | 60 | 10 | 0.25 | 30 | 0.75 | 10 | 0.25 | 10 | 0.25
|  | Total Effort |  |  | 1450
Notes: | [6 empty] | AK |  | BR |  | SB |  | BG
1 | Resoure | Role |  |  | Jun |  | 32 |  | 64 |  | 64 |  | 32 | 192
| AK: Azam Khan | Architect |  |  | Jul |  | 92 |  | 176 |  | 172 |  | 92 | 532
| BR: Bhaskar Reddy | Manager |  |  | Aug |  | 90 |  | 166 |  | 144 |  | 96 | 496
| SB: Suresh Byvarapu | Developer |  |  | Sep |  | 50 |  | 70 |  | 66 |  | 44 | 230
| BG: Balu Goud | Developer |  |  |  |  | 264 |  | 476 |  | 446 |  | 264
2 | Brought down the end date for Squaring and corner marking system end date to 12-Sep-2019 from 30-Sep-2019
3 | Total effort for Squaring and corner marking complete system is now at 1450 person hours. This is due to 1. Change in the Robotic chassis. Previous chassis comes with driver, control program, battery integrated. Need to implement all these in the new chassis. 2. User interface development (which was part of M4) has to be implemented now for interacting with the beacons, chassis using mobile BT terminal.
4 | As the tasks are taken up in parallel, there might be a need to order one more set of Robotic chassis some later.

## M1M2
|  |  | Projected effort(Person hours) |  |  | 9280 | 640 |  | 1200 |  | 1200 |  | 1200 |  | 1120 |  | 800 |  | 480 |  | 1120 |  | 1120 |  | 400
|  | Total planned effort(Person hours) |  |  |  | 862 | 280 |  | 124.8 |  | 128 |  | 94 |  | 200 |  | 36 |  | 0 |  | 200 |  | 0 |  | 0
|  |  | Effort for filtered tasks (Person hours): |  |  |  | 264 |  | 120 |  | 128 |  | 94 |  | 200 |  | 36 |  | 0 |  | 0 |  | 0 |  | 0
ROBOTIC PRINTER DEVELOPMENT PLAN | [26 empty] | Version: 0.8
Task ID | Task | Duration (Days) | Date |  | Milestone Effort (Hours) | Task Effort (Hours) | Resources | [19 empty] | Remarks/Comments
|  |  | From | To |  |  | AK |  | BR |  | SB |  | BG |  | E1 |  | E2 |  | E3 |  | M1 |  | A1 |  | T1
[7 empty] | Effort | Alloc | Effort | Alloc | Effort | Alloc | Effort | Alloc | Effort | Alloc | Effort | Alloc | Effort | Alloc | Effort | Alloc | Effort | Alloc | Effort | Alloc
T01 | LASER based distance measurement PoC (3' to 300' range) | 25 | 2019-06-10 | 2019-07-12 | 220
T0101 | Procure distance measurement laser, reflectors, laser cross hair, micontroller module | 2 | 2019-06-10 | 2019-06-11 |  | 8 | 8 | 0.5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0102 | Buy/Fabricate casing/base plate for corner reflectors | 2 | 2019-06-12 | 2019-06-13 |  | 20 |  | 1 |  | 0.3
T0103 | Study features, functionality and interfacing details of laser device | 5 | 2019-06-14 | 2019-06-20 |  | 40 | 20 | 0.5 | 10 | 0.25 | 10 | 0.25 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0104 | Study & development environment setup for nRF52840 Pro Mini Development board | 5 | 2019-06-21 | 2019-06-27 |  | 40 | 20 | 0.5 | 10 | 0.25 | 10 | 0.25 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0105 | Write program to control laser device for measuring distance | 5 | 2019-06-28 | 2019-07-04 |  | 40 | 20 | 0.5 | 0 |  | 0 |  | 20 | 0.5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0106 | Setup environment and measuring different distances from 3' to 300' | 3 | 2019-07-05 | 2019-07-09 |  | 36 | 12 | 0.5 | 24 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0107 | Check - Distance measurement accuracy (desired=3mm) achieved and submit report | 3 | 2019-07-10 | 2019-07-12 |  | 36 | 12 | 0.5 | 24 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0108 | Decide next steps based on distance measurement PoC | 0 | 2019-07-12 | 2019-07-12 | M1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 220
T02 | Corner marking and squaring subsystem PoC | 55 | 2019-07-15 | 2019-09-30 | 642 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0201 | Procure stepper motor for rotating lase device | 2 | 2019-07-15 | 2019-07-16 |  | 8 | 8 | 0.5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0202 | Procure mobile platform for carrying laser device | 2 | 2019-07-17 | 2019-07-18 |  | 8 | 8 | 0.5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0203 | Procure Line Laser markers | 2 | 2019-07-19 | 2019-07-22 |  | 8 | 8 | 0.5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0204 | Prepare mounting mechanism for laser device on stepper motor | 2 | 2019-07-23 | 2019-07-24 |  | 24 | 8 | 0.5 | 0 |  | 16 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0205 | Mechanical design for line laser device mounting on reflectors | 2 | 2019-07-25 | 2019-07-26 |  | 32 | 4 | 0.25 | 4 | 0.25 | 16 | 1 | 8 | 0.5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0206 | Prepare mounting mechanism for stepper motor on the platform | 3 | 2019-07-29 | 2019-07-31 |  | 36 | 6 | 0.25 | 0 |  | 24 | 1 | 6 | 0.25 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0207 | CAD implementation & fabrication of fixtures for stepper motor mounting | 2 | 2019-08-01 | 2019-08-02 |  | 24 | 4 | 0.25 | 4 | 0.25 | 8 | 0.5 | 8 | 0.5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0208 | Fabrication of mounting laser device, line laser and stepper motor | 3 | 2019-08-05 | 2019-08-07 |  | 48 | 6 | 0.25 | 6 | 0.25 | 24 | 1 | 12 | 0.5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0209 | Laser rotating system, Mobile platform and control electronics integration | 5 | 2019-08-08 | 2019-08-14 |  | 70 | 10 | 0.25 | 20 | 0.5 | 0 |  | 40 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0210 | Implementation of control program for laser device & mobile platform | 11 | 2019-08-16 | 2019-08-30 |  | 132 | 44 | 0.5 | 0 |  | 0 |  | 0 |  | 88 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0211 | Implementation of mobile platfom control program | 2 | 2019-09-02 | 2019-09-03 |  | 24 | 8 | 0.5 | 0 |  | 0 |  | 0 |  | 16 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0212 | Algorithm implementation for 2nd corner marking | 5 | 2019-09-04 | 2019-09-10 |  | 60 | 20 | 0.5 | 0 |  | 0 |  | 0 |  | 40 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0213 | Algorithm implementation for 3rd corner marking | 5 | 2019-09-11 | 2019-09-17 |  | 60 | 20 | 0.5 | 0 |  | 20 | 0.5 | 0 |  | 20 | 0.5 | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0214 | Algorithm implementation for 4th corner marking | 5 | 2019-09-18 | 2019-09-24 |  | 60 | 10 | 0.25 | 10 | 0.25 | 0 |  | 0 |  | 20 | 0.5 | 20 | 0.5 | 0 |  | 0 |  | 0 |  | 0
T0215 | Algorithm testing and sample squaring process trial | 4 | 2019-09-25 | 2019-09-30 |  | 48 | 8 | 0.25 | 8 | 0.25 | 0 |  | 0 |  | 16 | 0.5 | 16 | 0.5 | 0 |  | 0 |  | 0 |  | 0
T0215 | Decision on next steps based on corner marking and squaring subsystem PoC | 0 | 2019-09-30 | 2019-09-30 | M2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 862
Resources Details & Availability:
Initials & Name |  | Assignment | [11 empty] | Availability
AK | Azam Khan | System architecture and system design | [11 empty] | Available
BR | Bhaskar Reddy | System architecture and system design | [11 empty] | Available
SB | Suresh Bivarapu | Printer head control and printing | [11 empty] | Available
BG | Balaraj Goud | Mobile platform mobility control | [11 empty] | Available
T1 | Test Developer | Subsystem and system level test cases design and testing | [11 empty] | To be recruited
Product Readiness Milestones Highlights:
M2 | Layout squaring product will be ready by Mid-August with an accumulated effort of 874 person hours
Notes:
1 | Delay in component/equipment procument may delay the dependent tasks there by overall schedule. However, the resources will takeup other independent tasks during such situations and will try keeping the schedule on track.
Formulas:
To = [Date]+[Duration (Days)]-1
To = [Date]+[Duration (Days)]-1+2
Date = [Date, row above]
Date = [To, row above]+1

## M1_M5
|  |  | Projected effort(Person hours) |  |  | 9280 | 640 |  | 1200 |  | 1200 |  | 1200 |  | 1120 |  | 800 |  | 480 |  | 1120 |  | 1120 |  | 400
|  | Total planned effort(Person hours) |  |  |  | 8110 | 690 |  | 1148.8 |  | 1168 |  | 1092 |  | 820 |  | 732 |  | 548 |  | 820 |  | 636 |  | 644
|  |  | Effort for filtered tasks (Person hours): |  |  |  | 674 |  | 1144 |  | 1168 |  | 1092 |  | 820 |  | 732 |  | 548 |  | 652 |  | 636 |  | 644
ROBOTIC PRINTER DEVELOPMENT PLAN | [26 empty] | Version: 0.8
Task ID | Task | Duration (Days) | Date |  | Milestone Effort (Hours) | Task Effort (Hours) | Resources | [19 empty] | Remarks/Comments
|  |  | From | To |  |  | AK |  | BR |  | SB |  | BG |  | E1 |  | E2 |  | E3 |  | M1 |  | A1 |  | T1
[7 empty] | Effort | Alloc | Effort | Alloc | Effort | Alloc | Effort | Alloc | Effort | Alloc | Effort | Alloc | Effort | Alloc | Effort | Alloc | Effort | Alloc | Effort | Alloc
T01 | LASER based distance measurement PoC (3' to 300' range) | 25 | 2019-06-10 | 2019-07-12 | 220
T0101 | Procure distance measurement laser, reflectors, laser cross hair, micontroller module | 2 | 2019-06-10 | 2019-06-11 |  | 8 | 8 | 0.5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0102 | Buy/Fabricate casing/base plate for corner reflectors | 2 | 2019-06-12 | 2019-06-13 |  | 20 |  | 1 |  | 0.3
T0103 | Study features, functionality and interfacing details of laser device | 5 | 2019-06-14 | 2019-06-20 |  | 40 | 20 | 0.5 | 10 | 0.25 | 10 | 0.25 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0104 | Study & development environment setup for UBW32 board | 5 | 2019-06-21 | 2019-06-27 |  | 40 | 20 | 0.5 | 10 | 0.25 | 10 | 0.25 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0105 | Write program to control laser device for measuring distance | 5 | 2019-06-28 | 2019-07-04 |  | 40 | 20 | 0.5 | 0 |  | 0 |  | 20 | 0.5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0106 | Setup environment and measuring different distances from 3' to 300' | 3 | 2019-07-05 | 2019-07-09 |  | 36 | 12 | 0.5 | 24 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0107 | Check - Distance measurement accuracy (desired=3mm) achieved and submit report | 3 | 2019-07-10 | 2019-07-12 |  | 36 | 12 | 0.5 | 24 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0108 | Decide next steps based on distance measurement PoC | 0 | 2019-07-12 | 2019-07-12 | M1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 220
T02 | Corner marking and squaring subsystem PoC | 55 | 2019-07-15 | 2019-09-30 | 642 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0201 | Procure stepper motor for rotating lase device | 2 | 2019-07-15 | 2019-07-16 |  | 8 | 8 | 0.5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0202 | Procure mobile platform for carrying laser device | 2 | 2019-07-17 | 2019-07-18 |  | 8 | 8 | 0.5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0203 | Procure Line Laser markers | 2 | 2019-07-19 | 2019-07-22 |  | 8 | 8 | 0.5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0204 | Prepare mounting mechanism for laser device on stepper motor | 2 | 2019-07-23 | 2019-07-24 |  | 24 | 8 | 0.5 | 0 |  | 16 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0205 | Mechanical design for line laser device mounting on reflectors | 2 | 2019-07-25 | 2019-07-26 |  | 32 | 4 | 0.25 | 4 | 0.25 | 16 | 1 | 8 | 0.5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0206 | Prepare mounting mechanism for stepper motor on the platform | 3 | 2019-07-29 | 2019-07-31 |  | 36 | 6 | 0.25 | 0 |  | 24 | 1 | 6 | 0.25 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0207 | CAD implementation & fabrication of fixtures for stepper motor mounting | 2 | 2019-08-01 | 2019-08-02 |  | 24 | 4 | 0.25 | 4 | 0.25 | 8 | 0.5 | 8 | 0.5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0208 | Fabrication of mounting laser device, line laser and stepper motor | 3 | 2019-08-05 | 2019-08-07 |  | 48 | 6 | 0.25 | 6 | 0.25 | 24 | 1 | 12 | 0.5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0209 | Laser rotating system, Mobile platform and control electronics integration | 5 | 2019-08-08 | 2019-08-14 |  | 70 | 10 | 0.25 | 20 | 0.5 | 0 |  | 40 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0210 | Implementation of control program for laser device & mobile platform | 11 | 2019-08-16 | 2019-08-30 |  | 132 | 44 | 0.5 | 0 |  | 0 |  | 0 |  | 88 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0211 | Implementation of mobile platfom control program | 2 | 2019-09-02 | 2019-09-03 |  | 24 | 8 | 0.5 | 0 |  | 0 |  | 0 |  | 16 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0212 | Algorithm implementation for 2nd corner marking | 5 | 2019-09-04 | 2019-09-10 |  | 60 | 20 | 0.5 | 0 |  | 0 |  | 0 |  | 40 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0213 | Algorithm implementation for 3rd corner marking | 5 | 2019-09-11 | 2019-09-17 |  | 60 | 20 | 0.5 | 0 |  | 20 | 0.5 | 0 |  | 20 | 0.5 | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0214 | Algorithm implementation for 4th corner marking | 5 | 2019-09-18 | 2019-09-24 |  | 60 | 10 | 0.25 | 10 | 0.25 | 0 |  | 0 |  | 20 | 0.5 | 20 | 0.5 | 0 |  | 0 |  | 0 |  | 0
T0215 | Algorithm testing and sample squaring process trial | 4 | 2019-09-25 | 2019-09-30 |  | 48 | 8 | 0.25 | 8 | 0.25 | 0 |  | 0 |  | 16 | 0.5 | 16 | 0.5 | 0 |  | 0 |  | 0 |  | 0
T0215 | Decision on next steps based on corner marking and squaring subsystem PoC | 0 | 2019-09-30 | 2019-09-30 | M2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 862
T03 | XY gantry customization/design & fabrication for printing subsystem | 70 | 2019-10-01 | 2019-10-31 | 1506 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0301 | Gantry system procurement and study for necessary customizations | 2 | 2019-10-01 | 2019-10-02 |  | 32 | 0 |  | 16 | 1 | 0 |  | 16 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0302 | Battery and control electronic boards procurement & features study | 2 | 2019-10-03 | 2019-10-04 |  | 24 | 0 |  | 8 | 0.5 | 0 |  | 16 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0303 | Gantry customizations for fixing wheels, printing head, battery, squaring subsystem & electronics | 5 | 2019-10-07 | 2019-10-11 |  | 160 | 0 |  | 40 | 1 | 40 | 1 | 40 | 1 | 0 |  | 0 |  | 0 |  | 40 | 1 | 0 |  | 0
T0304 | CAD implementation and fabrication for gantry customizations | 5 | 2019-10-14 | 2019-10-18 |  | 120 | 10 | 0.25 | 20 | 0.5 | 40 | 1 | 10 | 0.25 | 0 |  | 0 |  | 0 |  | 40 | 1 | 0 |  | 0
T0305 | Gantry customizations fabrication and coordination, evaluation | 5 | 2019-10-21 | 2019-10-25 |  | 100 | 0 |  | 20 | 0.5 | 40 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 40 | 1 | 0 |  | 0
T0306 | Mecanum wheels & drives procurement for gantry system mobility | 4 | 2019-10-28 | 2019-10-31 |  | 96 | 0 |  | 32 | 1 | 32 | 1 | 32 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0307 | Fixture mechanism design for assembling wheels, battery and control electronics with gantry | 6 | 2019-10-01 | 2019-10-08 |  | 96 | 0 |  | 24 | 0.5 | 0 |  | 24 | 0.5 | 0 |  | 0 |  | 0 |  | 48 | 1 | 0 |  | 0
T0308 | CAD implementation & fabrication of fixtures for wheels, electronics, battery and gantry | 5 | 2019-10-11 | 2019-10-15 |  | 80 | 0 |  | 20 | 0.5 | 0 |  | 20 | 0.5 | 0 |  | 0 |  | 0 |  | 40 | 1 | 0 |  | 0
T0309 | Integration/assembly of gantry and wheels | 3 | 2019-10-18 | 2019-10-20 |  | 60 | 0 |  | 24 | 1 | 0 |  | 12 | 0.5 | 0 |  | 0 |  | 0 |  | 24 | 1 | 0 |  | 0
T0310 | Gantry system mobility-wheel drive front-back control program implementation | 5 | 2019-10-01 | 2019-10-05 |  | 100 | 0 |  | 20 | 0.5 | 40 | 1 | 20 | 0.5 | 0 |  | 0 |  | 0 |  | 20 | 0.5 | 0 |  | 0
T0311 | Gantry mobility-wheel drive for side-ways movement control program implementation | 2 | 2019-10-06 | 2019-10-09 |  | 32 | 0 |  | 8 | 0.5 | 8 | 0.5 | 16 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0312 | Gantry system diagonal movement control program implementation | 3 | 2019-10-12 | 2019-10-14 |  | 48 | 0 |  | 12 | 0.5 | 12 | 0.5 | 24 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0313 | Gantry system mobility orientation control algorithm implementation | 3 | 2019-10-15 | 2019-10-19 |  | 48 | 12 | 0.5 | 12 | 0.5 | 24 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0314 | Application development for controlling gantry mobility and position | 15 | 2019-10-01 | 2019-10-21 |  | 360 | 0 |  | 0 |  | 60 | 0.5 | 60 | 0.5 | 60 | 0.5 | 60 | 0.5 | 0 |  | 0 |  | 120 | 1 | 0
T0315 | Gantry system mobility control testing and performance evaluation | 5 | 2019-10-22 | 2019-10-28 |  | 150 | 10 | 0.25 | 40 | 1 | 20 | 0.5 | 40 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 40 | 1
T0316 | Decision on further steps based on gantry performance and positioning accuracy | 0 | 2019-10-31 | 2019-10-31 | M3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2368
T04 | Ink jet printing head integration with xy-gantry & performing un-guided printing | 116 | 2019-10-01 | 2019-12-06 | 2790 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0401 | Ink-jet printing head system procurement | 3 | 2019-10-01 | 2019-10-03 |  | 36 | 0 |  | 24 | 1 | 12 | 0.5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0402 | Print head features/functionality study, interface analysis, mechanism for custom interfacing | 6 | 2019-10-04 | 2019-10-11 |  | 144 | 24 | 0.5 | 24 | 0.5 | 0 |  | 48 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 48 | 1
T0403 | Mechanism for print head fixture with gantry (ideas and feasibility study) | 5 | 2019-10-14 | 2019-10-18 |  | 140 | 20 | 0.5 | 20 | 0.5 | 20 | 0.5 | 0 |  | 20 | 0.5 | 20 | 0.5 | 0 |  | 40 | 1 | 0 |  | 0
T0404 | CAD design and fabrication fixture of print head and control electronics with gantry | 5 | 2019-10-21 | 2019-10-25 |  | 160 | 0 |  | 0 |  | 20 | 0.5 | 20 | 0.5 | 40 | 1 | 0 |  | 20 | 0.5 | 40 | 1 | 20 | 0.5 | 0
T0405 | Print head interfacing hardware design with custom boards | 4 | 2019-10-28 | 2019-10-31 |  | 128 | 0 |  | 16 | 0.5 | 16 | 0.5 | 16 | 0.5 | 16 | 0.5 | 16 | 0.5 | 16 | 0.5 | 0 |  | 32 | 1 | 0
T0406 | Print head movement control algorithm development (embedded code implementation) | 10 | 2019-11-01 | 2019-11-14 |  | 200 | 0 |  | 40 | 0.5 | 40 | 0.5 | 40 | 0.5 | 40 | 0.5 | 0 |  | 40 | 0.5 | 0 |  | 0 |  | 0
T0407 | Application development for selection and loading of layout plan to printing subsystem | 8 | 2019-10-01 | 2019-10-10 |  | 128 | 0 |  | 32 | 0.5 | 32 | 0.5 | 0 |  | 64 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0408 | Printing head input data format study and understanding coordination with supplier | 8 | 2019-10-11 | 2019-10-22 |  | 192 | 32 | 0.5 | 32 | 0.5 | 64 | 1 | 0 |  | 0 |  | 32 | 0.5 | 0 |  | 0 |  | 32 | 0.5 | 0
T0409 | Layout image format study and understanding | 5 | 2019-10-01 | 2019-10-07 |  | 60 | 0 |  | 20 | 0.5 | 20 | 0.5 | 20 | 0.5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0410 | Layout plan image processing alogorithm for convering to printer friendly format | 10 | 2019-10-08 | 2019-10-21 |  | 120 | 0 |  | 40 | 0.5 | 40 | 0.5 | 40 | 0.5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0411 | Identify and setup printing experimentation area for printing sample layout | 3 | 2019-10-22 | 2019-10-26 |  | 24 | 12 | 0.5 | 12 | 0.5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0412 | Printing functionality comprehensive test plan development | 12 | 2019-10-01 | 2019-10-16 |  | 384 | 48 | 0.5 | 48 | 0.5 | 48 | 0.5 | 48 | 0.5 | 48 | 0.5 | 48 | 0.5 | 0 |  | 0 |  | 0 |  | 96 | 1
T0413 | Printing functionality comprehensive test scenaios & test cases generation | 12 | 2019-10-17 | 2019-11-01 |  | 384 | 48 | 0.5 | 0 |  | 0 |  | 48 | 0.5 | 0 |  | 48 | 0.5 | 96 | 1 | 48 | 0.5 | 0 |  | 96 | 1
T0414 | Printing functionality comprehensive test cases design | 15 | 2019-11-04 | 2019-11-22 |  | 390 | 30 | 0.25 | 0 |  | 0 |  | 60 | 0.5 | 60 | 0.5 | 60 | 0.5 | 60 | 0.5 | 0 |  | 60 | 0.5 | 60 | 0.5
T0415 | Printing functionality testing with sample layout image | 5 | 2019-11-25 | 2019-11-29 |  | 180 | 0 |  | 20 | 0.5 | 0 |  | 40 | 1 | 0 |  | 40 | 1 | 40 | 1 | 0 |  | 0 |  | 40 | 1
T0416 | Printing performance evaluation, re-testing & report generation | 5 | 2019-12-02 | 2019-12-06 |  | 120 | 20 | 0.5 | 20 | 0.5 | 40 | 1 | 20 | 0.5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 20 | 0.5
T0417 | Decision on further steps based on printing performance | 0 | 2019-12-06 | 2019-12-06 | M4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 5158
T05 | System integration-squaring subsystem integration with printing subsystem | 115 | 2019-11-04 | 2020-02-07 | 2952 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0501 | GSM/GPRS modules and adapters procurement | 2 | 2019-11-04 | 2019-11-05 |  | 16 | 0 |  | 16 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0502 | Deciding fixture mechanism for squaring subsystem with gantry (printing subsystem) | 2 | 2019-11-04 | 2019-11-05 |  | 24 | 8 | 0.5 | 16 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0503 | CAD implementation & fabrication of fixture for squaring subsystem with gantry | 5 | 2019-11-06 | 2019-11-12 |  | 80 | 20 | 0.5 | 20 | 0.5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 40 | 1 | 0 |  | 0
T0504 | GSM/GPRS interface software implementation | 10 | 2019-11-06 | 2019-11-19 |  | 200 | 0 |  | 40 | 0.5 | 40 | 0.5 | 0 |  | 40 | 0.5 | 40 | 0.5 | 0 |  | 0 |  | 40 | 0.5 | 0
T0505 | Develop cloud interface for the system | 10 | 2019-11-20 | 2019-12-03 |  | 200 | 0 |  | 40 | 0.5 | 40 | 0.5 | 0 |  | 0 |  | 40 | 0.5 | 0 |  | 40 | 0.5 | 40 | 0.5 | 0
T0506 | Integrating squaring subsystem hardware with gantry (printing subsystem) | 5 | 2019-12-04 | 2019-12-10 |  | 80 | 20 | 0.5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 40 | 1 | 0 |  | 20 | 0.5
T0507 | Integrating squaring subsystem software and gatry mobility software | 5 | 2019-12-11 | 2019-12-17 |  | 100 | 0 |  | 20 | 0.5 | 40 | 1 | 0 |  | 20 | 0.5 | 0 |  | 0 |  | 0 |  | 0 |  | 20 | 0.5
T0508 | Squaring algorithm testing with sample layout image and corrections in the software if needed | 5 | 2019-12-18 | 2019-12-24 |  | 80 | 20 | 0.5 | 20 | 0.5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 40 | 1
T0509 | Integrating printing head control software (with squaring and gantry mobility software) | 3 | 2019-12-26 | 2019-12-30 |  | 48 | 12 | 0.5 | 12 | 0.5 | 0 |  | 24 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
T0510 | Layout image processing algorithm software integration | 5 | 2019-11-04 | 2019-11-08 |  | 140 | 0 |  | 20 | 0.5 | 0 |  | 20 | 0.5 | 0 |  | 20 | 0.5 | 40 | 1 | 0 |  | 20 | 0.5 | 20 | 0.5
T0511 | Layout plan image processing alogorithm for partitioning the layout into sections | 5 | 2019-11-11 | 2019-11-15 |  | 140 | 0 |  | 20 | 0.5 | 0 |  | 20 | 0.5 | 40 | 1 | 20 | 0.5 | 0 |  | 0 |  | 40 | 1 | 0
T0512 | Layout printing algorithm for printing from any part of the print area | 12 | 2019-11-18 | 2019-12-03 |  | 432 | 0 |  | 48 | 0.5 | 48 | 0.5 | 48 | 0.5 | 96 | 1 | 48 | 0.5 | 48 | 0.5 | 0 |  | 96 | 1 | 0
T0513 | Algorithm implementation for resuming the printing where it was left before | 12 | 2019-12-04 | 2019-12-19 |  | 432 | 0 |  | 48 | 0.5 | 96 | 1 | 96 | 1 | 0 |  | 96 | 1 | 0 |  | 0 |  | 96 | 1 | 0
T0514 | Algorithm implementation for drain and water pipes detection using laser based scanning | 12 | 2019-12-20 | 2020-01-07 |  | 216 | 24 | 0.25 | 0 |  | 48 | 0.5 | 0 |  | 0 |  | 48 | 0.5 | 48 | 0.5 | 0 |  | 0 |  | 48 | 0.5
T0515 | Algorithm implementaion for gantry system alignment with the squared area | 5 | 2020-01-08 | 2020-01-15 |  | 120 | 0 |  | 0 |  | 20 | 0.5 | 40 | 1 | 0 |  | 20 | 0.5 | 20 | 0.5 | 40 | 1 | 0 |  | 0
T0516 | Testing the squaring and printing process with combined single system | 2 | 2020-01-16 | 2020-01-17 |  | 56 | 8 | 0.5 | 8 | 0.5 | 0 |  | 0 |  | 8 | 0.5 | 0 |  | 0 |  | 16 | 1 | 0 |  | 16 | 1
T0517 | Testing the printing from any random position within the marked area after squaring process completed | 5 | 2020-01-20 | 2020-01-24 |  | 260 | 20 | 0.5 | 20 | 0.5 | 0 |  | 20 | 0.5 | 40 | 1 | 40 | 1 | 40 | 1 | 40 | 1 | 0 |  | 40 | 1
T0518 | Testing of obstacle detection (drain and water pipes) | 2 | 2020-01-27 | 2020-01-28 |  | 64 | 0 |  | 0 |  | 0 |  | 0 |  | 16 | 1 | 0 |  | 16 | 1 | 16 | 1 | 0 |  | 16 | 1
T0519 | Performance evaluation and report generation | 3 | 2020-01-29 | 2020-01-31 |  | 84 | 12 | 0.5 | 12 | 0.5 | 0 |  | 0 |  | 12 | 0.5 | 0 |  | 24 | 1 | 0 |  | 0 |  | 24 | 1
T0520 | User manuals and other support documentation | 5 | 2020-02-03 | 2020-02-07 |  | 180 | 0 |  | 20 | 0.5 | 40 | 1 | 0 |  | 0 |  | 0 |  | 40 | 1 | 40 | 1 | 40 | 1 | 0
T0521 | Decision on further steps based on over all system performance | 0 | 2020-02-07 | 2020-02-07 | M5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 8110
Resources Details & Availability:
Initials & Name |  | Assignment | [11 empty] | Availability
AK | Azam Khan | System architecture and system design | [11 empty] | Available
BR | Bhaskar Reddy | System architecture and system design | [11 empty] | Available
SB | Suresh Bivarapu | Printer head control and printing | [11 empty] | Available
BG | Balaraj Goud | Mobile platform mobility control | [11 empty] | Available
T1 | Test Developer | Subsystem and system level test cases design and testing | [11 empty] | To be recruited
M1 | Mechanical Designer (CAD) | Mechanical design, Other support related mechanical hardware | [11 empty] | To be recruited
A1 | Application Developer | System level application development, Layout image processing, user interface development | [11 empty] | To be recruited
E1 | Embedded Developer 1 | Laser control and measurement software | [11 empty] | To be recruited
E2 | Embedded Developer 2 | Mobile platform mobility control | [11 empty] | To be recruited
E3 | Embedded Developer 3 | Printer head control and printing | [11 empty] | To be recruited
Product Readiness Milestones Highlights:
M2 | Layout squaring product will be ready by Mid-August with an accumulated effort of 874 person hours
M4 | Layout squaring product and Layout printing without obstacle detection will be ready by mid-November with an accumulated effort of 5098 person hours
M5 | Layout squaring product and Layout printing with obstacle detection will be ready by end-December with an accumulated effort of 8010 person hours
Notes:
1 | Delay in component/equipment procument may delay the dependent tasks there by overall schedule. However, the resources will takeup other independent tasks during such situations and will try keeping the schedule on track.
Formulas:
To = [Date]+[Duration (Days)]-1
To = [Date]+[Duration (Days)]-1+2
Date = [Date, row above]
Date = [To, row above]+1

## PS
Robotic Printer Development Plan – Milestone Summary
Milestone ID | Milestone Description | No. of Working Days | Start Date | End Date | Milestone Effort (PHs) | Cummulative Effort (PHs)
M1 | LASER based distance measurement PoC (3' to 300' range) | 25 | 2019-06-10 | 2019-07-12 | 220 | 220
M2 | Corner marking and squaring subsystem PoC | 55 | 2019-07-15 | 2019-09-30 | 642 | 862
M3 | XY gantry customization/design & fabrication for printing subsystem | 70 | 2019-10-01 | 2019-10-31 | 1506 | 2368
M4 | Ink jet printing head integration with xy-gantry & performing un-guided printing | 116 | 2019-10-01 | 2019-12-06 | 2790 | 5158
M5 | System integration-squaring subsystem integration with printing subsystem | 115 | 2019-11-04 | 2020-02-07 | 2952 | 8110
|  |  | Total Effort (PHs) |  | 8110
Notes:
PHs: Person Hours

## EB
Monthly Resource Loading(Hours)
| Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Resource Loading
Azam Khan | 68 | 66 | 64 | 66 | 216 | 58 | 96 | 40 |  | 674
Bhaskar Reddy | 20 | 52 | 30 | 18 | 564 | 280 | 120 | 40 | 20 | 1144
Suresh Bivarapu | 20 | 56 | 32 | 20 | 588 | 168 | 224 | 20 | 40 | 1168
Balaraj Goud | 20 | 14 | 60 |  | 570 | 228 | 140 | 60 |  | 1092
Embedded Developer 1 |  |  | 88 | 112 | 248 | 276 | 20 | 76 |  | 820
Embedded Developer 2 | Sep: 36; Oct: 224; Nov: 268; Dec: 144; Jan: 60 | 732
Embedded Developer 3 | Oct: 132; Nov: 228; Dec: 48; Jan: 100; Feb: 40 | 548 |  |  | 8 |  | Jun | Jul | Aug | Sep
Mechanical Designer 1 | Oct: 380; Nov: 80; Dec: 40; Jan: 112; Feb: 40 | 652 | M1M2 |  |  |  | 8 | 23 | 21 | 9 | 61
Application Developer 1 | Oct: 204; Nov: 296; Dec: 96; Feb: 40 | 636 | #of resources | 3 |  | AK | 32 | 92 | 84 | 36
Tester | Oct: 280; Nov: 120; Dec: 148; Jan: 96 | 644 | #months | 3 |  | BR | 64 | 184 | 168 | 72
Monthly Total Load | 128 | 188 | 274 | 252 | 3406 | 2002 | 1076 | 604 | 180 | 8110 | ph/month | 160 |  | SB | 64 | 184 | 168 | 72
Process & management % | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  |  | 1440 | 862 |  | 1281
+Process & Management | 12.8 | 18.8 | 27.4 | 25.2 | 340.6 | 200.2 | 107.6 | 60.4 | 18 | 811 | Diff | 578
Invoiced person hours
| Jun: Full duration effort (Person Hours) | 8921
Monthly Resource Loading(Hours) | bar: Jun to Jan
| May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Azam Khan | 84 | 96 | 92 | 90 | 92 | 86 | 92 | 76 | 708
Bhaskar Reddy | 84 | 176 | 168 | 160 | 176 | 100 | 164 | 144 | 1172
Suresh Bivarapu | 80 | 172 | 164 | 164 | 172 | 120 | 168 | 136 | 1176
Balaraj Goud | 80 | 166 | 160 | 148 | 168 | 96 | 152 | 120 | 1090
Embedded Developer 1 |  |  | 164 | 148 | 152 | 124 | 156 | 112 | 856
Embedded Developer 2 |  |  |  | 148 | 168 | 116 | 168 | 96 | 696
Embedded Developer 3 | Sep: 168; Oct: 84; Nov: 168; Dec: 120 | 540
Mechanical Designer 1 |  | 88 | 164 |  | 168 |  | 80 | 128 | 628
Application Developer 1 |  |  |  | 120 | 140 | 92 | 156 | 136 | 644
Tester |  |  |  | 136 | 144 | 96 | 148 | 144 | 668
Monthly Total Load | 328 | 698 | 912 | 1114 | 1548 | 914 | 1452 | 1212
Process & management % | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
+Process & Management | 360.8 | 767.8 | 1003.2 | 1225.4 | 1702.8 | 1005.4 | 1597.2 | 1333.2
Invoiced person hours
| May: Full duration effort (Person Hours) | 8178